## Supabase Islemleri
# | Faz | Is | Durum | Tablo / Icerik | Satir Sayisi | Disk (GB) | Tahmini Sure | Not
TAMAMLANAN ISLEMLER
1 | Faz 0 | B-002 Schema v1 (12 tablo DDL + RLS + trigger + enum) | TAMAMLANDI | 12 tablo DDL | - | - | <5 dk | 2026-04-29
2 | Faz 0 | B-003 Static facts upload | TAMAMLANDI | dim_theme, fact_theme_year_agg, fact_gap_matrix, dim_theme_embedding, fact_method_list | 562,931 | <1 | ~15 dk | 2026-04-29
3 | Faz 1 | B-008 PaperCard upload | TAMAMLANDI | fact_paper_id_card | 24,862,232 | ~10 | ~55 dk | 2026-04-30, 2XL compute
4 | Faz 1 | B-008 GhostCard upload | TAMAMLANDI | dim_ghost_paper | 31,855,437 | ~18 | ~50 dk | 2026-04-30, 2XL compute
B-013 FAZ 2 — SATELLITE TABLOLAR (SIRADAKI)
5 | Faz 2 | Migration 0004 uygula (DDL) | TAMAMLANDI | 3 tablo DDL + index + RLS | - | - | <1 dk | 2026-05-10, DDL uygulanmis (bagimli tablolar dolu)
6 | Faz 2 | fact_paper_sentence_role upload | TAMAMLANDI | fact_paper_sentence_role | 24,862,264 | ~1.5 | ~20 dk | 2026-05-10, Supabase'de aktif
7 | Faz 2 | fact_paper_d_estra upload | TAMAMLANDI | fact_paper_d_estra | 24,862,288 | ~1.5 | ~25 dk | 2026-05-10, Supabase'de aktif
8 | Faz 2 | fact_paper_ref_age upload | TAMAMLANDI | fact_paper_ref_age | 16,696,388 | ~0.5 | ~15 dk | 2026-05-10, Supabase'de aktif
9 | Faz 2 | Faz 2 Verify (row count + histogram + quantile) | BEKLIYOR | Dogrulama | - | - | <5 dk | Notebook Cell 8
FAZ 3 — WAREHOUSE MIRROR (12 TABLO, MIGRATION 0005-0008)
10 | Faz 3 | Migration 0005 yazimi (ESTRA cekirdek DDL) | TAMAMLANDI | quality_v3 + w_estra + velocity | - | - | ~30 dk | 2026-05-10, DDL uygulanmis (bagimli tablolar dolu)
11 | Faz 3 | fact_paper_quality_v3 upload | TAMAMLANDI | fact_paper_quality_v3 | 24,862,296 | ~1 | ~12 dk | 2026-05-10, Supabase'de aktif
12 | Faz 3 | fact_paper_w_estra upload | TAMAMLANDI | fact_paper_w_estra | 24,011,812 | ~3 | ~40 dk | 2026-05-10, Supabase'de aktif
13 | Faz 3 | fact_paper_velocity upload | TAMAMLANDI | fact_paper_velocity | 22,998,974 | ~1.5 | ~15 dk | 2026-05-10, Supabase'de aktif
14 | Faz 3 | Migration 0006 yazimi (Metadata + Gate DDL) | TAMAMLANDI | field + interdisc + topic + metod + replication | - | - | ~30 dk | 2026-05-10, DDL uygulanmis (bagimli tablolar dolu)
15 | Faz 3 | fact_paper_field upload | TAMAMLANDI | fact_paper_field | 24,865,280 | ~0.8 | ~10 dk | 2026-05-10, Supabase'de aktif
16 | Faz 3 | fact_paper_interdisc upload | TAMAMLANDI | fact_paper_interdisc | 23,992,792 | ~1.2 | ~15 dk | 2026-05-10, Supabase'de aktif
17 | Faz 3 | fact_paper_topic upload (rank<=3) | TAMAMLANDI | fact_paper_topic | 65,987,776 | ~1 | ~30 dk | 2026-05-10, Supabase'de aktif
18 | Faz 3 | fact_paper_metod upload | TAMAMLANDI | fact_paper_metod | 49,994,492 | ~0.5 | ~30 dk | 2026-05-10, Supabase'de aktif
19 | Faz 3 | dim_paper_replication upload | TAMAMLANDI | dim_paper_replication | 24,003,996 | ~0.3 | ~5 dk | 2026-05-10, Supabase'de aktif
20 | Faz 3 | Migration 0007 yazimi (Advisor + Centrality DDL) | TAMAMLANDI | method_topic_affinity + centrality | - | - | ~15 dk | 2026-05-10, DDL uygulanmis (bagimli tablolar dolu)
21 | Faz 3 | fact_method_topic_affinity upload | TAMAMLANDI | fact_method_topic_affinity | 65,061 | <0.1 | <1 dk | 2026-05-10, Supabase'de aktif
28 | Faz 3 | fact_method_field_affinity upload | TAMAMLANDI | fact_method_field_affinity | 390 | <0.1 | <1 dk | 2026-05-10, kucuk tablo, Supabase'de aktif
22 | Faz 3 | fact_paper_centrality upload | TAMAMLANDI | fact_paper_centrality | 21,154,920 | ~2 | ~25 dk | 2026-05-10, Supabase'de aktif
23 | Faz 3 | Migration 0008 yazimi (Komsu + Author DDL) | TAMAMLANDI | bibcoupling_top50 + dim_author | - | - | ~15 dk | 2026-05-10, DDL uygulanmis (bagimli tablolar dolu)
24 | Faz 3 | fact_paper_bibcoupling_top50 upload | TAMAMLANDI | fact_paper_bibcoupling_top50 | 643,353,344 | ~8 | ~3 saat | 2026-05-10, Supabase'de aktif
25 | Faz 3 | dim_author upload | TAMAMLANDI | dim_author | 22,645,678 | ~4 | ~90 dk | 2026-05-10, Supabase'de aktif
26 | Faz 3 | Faz 3 Verify (tum tablolar) | BEKLIYOR | Row count + FK + index sanity | - | - | ~15 dk
27 | Faz 3 | Compute 4XL -> Small dusur | BEKLIYOR | Kalici tasarruf | - | - | <5 dk | Tum upload bittikten sonra

## RAG Mimari
# | Katman / Servis | Dosya | Real Impl Sınıf | Mock Impl | Model / Kaynak | Sıralama | Çağıran Endpoint | Kanıt | Durum
═══ ANA RAG PIPELINE — 6 KATMAN (search.py:4 sıralama) ═══
L1 | Listener | api/services/listener.py | GeminiListener | MockListener | Gemini Flash 2.5 (LiteLLM) | 1 | /api/search, /api/top5 | A: search.py:33,46-50 + top5.py | LIVE
L2 | Anchor | api/services/anchor.py | OpenAlexAnchor | MockAnchor | OpenAlex API + (anchor_finder for /research-area) | 2 | /api/search, /api/top5 | A: search.py:31 + top5.py | LIVE
L3 | PoolRouter | api/services/pool_router.py | HybridPoolRouter | MockPoolRouter | Pinecone (papers-bgem3, dense+sparse RRF k=60) | 3 | /api/search, /api/top5 | A: search.py:34 + top5.py | LIVE
L4 | Reranker | api/services/reranker.py | BgeReranker | MockReranker | BGE-v2-m3 (HF Endpoint) | 4 | /api/search, /api/top5 | A: search.py:35 + top5.py | LIVE
L5 | Curator | api/services/curator.py | OutlinesCurator + _fetch_paper_cards | (yok) | Gemini Pro 2.5 + structured output | 5 | /api/search, /api/top5, /api/paper-detail | A: search.py:32 + top5.py + paper_detail.py | LIVE
L6 | Presenter | api/services/presenter.py | (import edilmiyor) | — | TBD | 6 (planlı) | (hiçbir route import etmiyor) | A: grep — sıfır match | YETIM/PLANLI
═══ YAN SERVİSLER (RAG'ı destekleyen) ═══
S1 | anchor_finder (F9 P095) | api/services/anchor_finder.py | 3 çapa adayı orkestrasyonu | — | OpenAlex + Pinecone | — | /api/research-area | A: research_area.py + anchor_finder.py:1 | LIVE
S2 | faithfulness_gate | api/services/faithfulness_gate.py | (içerik doğrulanmadı) | — | TBD | post-Curator | search response faithfulness_meta | A: search.py:5 'faithfulness_meta' + dosya var; içerik C | LIVE (partial)
S3 | litellm_router | api/services/litellm_router.py | Flash/Pro routing | — | Gemini Flash 2.5 / Pro 2.5 | Listener+Curator içi | (katmanlar tarafından) | A: dosya var; davranış C | LIVE
S4 | llm_service | api/services/llm_service.py | call() + LLMServiceError | — | LiteLLM wrapper | — | /api/q, /api/chat, /api/summarize, /api/research-area, /api/diary, /api/workshop | A: 6 route import | LIVE
S5 | translator | api/services/translator.py | (içerik doğrulanmadı) | — | TBD | — | (role_modules/translate_query?) | A: dosya var; bağlantı C | LIVE
S6 | openalex_polite | api/services/openalex_polite.py | polite-pool wrapper | — | OpenAlex API | — | /api/q, /api/enrich (B-49) | A: q.py:34 + enrich.py:56 | LIVE
S7 | elevenlabs_tts | api/services/elevenlabs_tts.py | (içerik doğrulanmadı) | — | ElevenLabs API (Q2 açık) | — | /api/tts | A: dosya var; karar açık | LIVE (Q2)
S8 | diary_service | api/services/diary_service.py | (içerik doğrulanmadı) | — | — | — | /api/diary | A: diary.py:import | LIVE
S9 | progress_service | api/services/progress_service.py | (içerik doğrulanmadı) | — | — | — | /api/workshop | A: workshop.py:import | LIVE
S10 | bibliometric_service | api/services/bibliometric_service.py | (içerik doğrulanmadı) | — | OpenAlex aggregates? | — | /api/projects/{id}/bibliometrics | A: dosya var | LIVE
═══ ROLE MODULES (api/services/role_modules/) — 10 modül ═══
R1 | vitrin_summary | role_modules/vitrin_summary.py | — | — | Gemini (Vitrin Q ~400 kelime K=12) | — | /api/q (?) | A: dosya var; bağlantı C | LIVE
R2 | vitrin_literature | role_modules/vitrin_literature.py | — | — | Gemini (Vitrin Q3 K=25 7-tag) | — | /api/q2 veya /api/literature-review | A: dosya var | LIVE
R3 | librarian | role_modules/librarian.py | — | — | Gemini | — | /api/research-area | A: research_area.py:import | LIVE
R4 | advisor_summary | role_modules/advisor_summary.py | — | — | Gemini | — | (workshop?) | A: dosya var; bağlantı C | LIVE
R5 | diary_pre_advisor | role_modules/diary_pre_advisor.py | — | — | Gemini | — | /api/diary | A: dosya var | LIVE
R6 | topic_exploration | role_modules/topic_exploration.py | — | — | Gemini | — | /api/topic/suggest (?) | A: dosya var; bağlantı C | LIVE
R7 | method_selection | role_modules/method_selection.py | — | — | Gemini | — | (workshop?) | A: dosya var | LIVE
R8 | translate_query | role_modules/translate_query.py | — | — | Gemini | — | (Listener içi?) | A: dosya var | LIVE
R9 | gap_heatmap | role_modules/gap_heatmap.py | — | — | Gemini | — | /api/gap-heatmap | A: dosya var; route'da import yok | LIVE (?)
═══ CACHE TOPOLOJİSİ ═══
C1 | Redis L1 (q) | api/db/redis_client.py | cache_get/cache_set + CacheNamespace | — | Redis (Upstash? — Q açık) | — | /api/search (1h TTL) | A: search.py:22 + redis_client.py | LIVE
C2 | Edge cache (Vercel) | — | — | — | Next.js fetch revalidate | — | Backend Endpoints 'Cache' kolonu (edge 5min/60s/24h) | B: BE sheet | PLANLI
═══ PLANLI (henüz dosya yok) ═══
P1 | engine/ klasörü | engine/ (PLANLI) | — | — | — | — | Saf core (CLAUDE.md §5) | B: CLAUDE.md §5 + ls — yok | PLANLI
P2 | estra_scorer | engine/estra_scorer.py (PLANLI) | — | — | — | — | Models'da kavram geçiyor | B: search/project/bibliometric/gap_profile models | PLANLI
P3 | cluster_expander | engine/cluster_expander.py (PLANLI) | — | — | — | — | anchor_finder ile bağlantılı | B: anchor_finder.py | PLANLI
P4 | F9 P096 anchor lock state machine | — | — | — | — | — | anchor.py + project_topics tablosu | B: F1 master plan §6 + memory canon | PLANLI
P5 | Presenter implementasyonu | api/services/presenter.py | (import edilmiyor) | — | Gemini Pro 2.5 | 6 | — | A: dosya var, 0 import | PLANLI

## Acik Kararlar
# | Başlık | Bağlı Sheet | Bağlı Satır | Karar (boş — sonra)
═══ AUTH & TIER (Clerk geçişi) ═══
AT-1 | AQ-1 — Tier başına günlük arama / LLM çağrı / disk / proje limiti sayıları | Auth & Tier | AQ-* / matris
AT-2 | AQ-2 — Anonim kullanıcı (login öncesi) hangi endpoint'lere erişebilir? | Auth & Tier | AQ-* / matris
AT-3 | AQ-3 — Clerk webhook signing secret rotation politikası | Auth & Tier | AQ-* / matris
AT-4 | AQ-4 — Mevcut Supabase RLS policies (auth.uid() kullanan) refactor planı | Auth & Tier | AQ-* / matris
AT-5 | AQ-5 — Onboarding'te tier nasıl seçilir? (default ogrenci → upgrade flow) | Auth & Tier | AQ-* / matris
AT-6 | AT-tier-quota — 3 tier × 4 limit (arama/LLM/paper/proje) = 12 hücre TBD | Auth & Tier | AQ-* / matris
═══ CRON & SCHEDULED (F13 Q3) ═══
CR-1 | Q3 — Cron provider seçimi: Render scheduled / Supabase cron / GitHub Actions | Cron & Scheduled | AQ-C1 / C-3..C-8
CR-2 | C-3 — F13 cron #1: isim + frequency + sorumluluk | Cron & Scheduled | AQ-C1 / C-3..C-8
CR-3 | C-4 — F13 cron #2: isim + frequency + sorumluluk | Cron & Scheduled | AQ-C1 / C-3..C-8
CR-4 | C-5 — F13 cron #3: isim + frequency + sorumluluk | Cron & Scheduled | AQ-C1 / C-3..C-8
CR-5 | C-6 — F13 cron #4: isim + frequency + sorumluluk | Cron & Scheduled | AQ-C1 / C-3..C-8
CR-6 | C-7 — F13 cron #5: isim + frequency + sorumluluk | Cron & Scheduled | AQ-C1 / C-3..C-8
CR-7 | C-8 — F13 cron #6: isim + frequency + sorumluluk | Cron & Scheduled | AQ-C1 / C-3..C-8
═══ DEPLOY & INFRA ═══
DP-1 | D-1 — Vercel plan: Hobby ($0) mu Pro ($20/ay) mu | Deploy & Infra | D-1..D-13
DP-2 | D-2 — Render plan: Free mı Starter ($7/ay) mı + ALWAYS-on garantisi | Deploy & Infra | D-1..D-13
DP-3 | D-3 — Supabase region (EU TBD) + Pro upgrade ne zaman ($25/ay) | Deploy & Infra | D-1..D-13
DP-4 | D-5 — HF Endpoint EU region kararı + scale config + cold start tolerance | Deploy & Infra | D-1..D-13
DP-5 | D-7 — Clerk plan: Free 10K MAU mı Pro $25/ay mı | Deploy & Infra | D-1..D-13
DP-6 | D-12 — Error tracking: Sentry mı, Logflare mı, kendi log mu | Deploy & Infra | D-1..D-13
DP-7 | D-13 — Cache (Redis): Upstash mı, kullanılacak mı, hangi endpoint'ler | Deploy & Infra | D-1..D-13
═══ HATA & LIMIT ═══
HL-1 | EQ-1 — Tier × rate limit sayıları (req/sec, req/dk, req/gün) | Hata & Limit | EQ-1..3 / E-*
HL-2 | EQ-2 — Error tracking provider (D-12 ile bağlı) | Hata & Limit | EQ-1..3 / E-*
HL-3 | EQ-3 — Idempotency key standardı: write endpoint'lerde X-Idempotency-Key zorunlu mu | Hata & Limit | EQ-1..3 / E-*
HL-4 | E-1..E-8 — Endpoint başına retry policy + circuit breaker eşikleri | Hata & Limit | EQ-1..3 / E-*
═══ DİĞER (F13 Q1, Q2, Q4 — F13 plan) ═══
OT-1 | Q1 — Cohere reranker: kullanılacak mı, alternatif (HF BGE-v2-m3) yeterli mi | (F13 plan) | Q1/Q2/Q4
OT-2 | Q2 — ElevenLabs TTS: kullanılacak mı, alternatif (Cosmos TR) yeterli mi | (F13 plan) | Q1/Q2/Q4
OT-3 | Q4 — Mail provider: Resend/SendGrid/SMTP — Clerk webhook ile entegrasyon | (F13 plan) | Q1/Q2/Q4

## Pivot Kararlari (B-021)
# | Karar ID | Karar | Durum | Kapsam | MVP/Post-MVP | Ek Sure | Not
ETKILESIM MODELI PIVOTU
1 | DM-017 | Chat-first hybrid default | ONAYLANDI | /search chat input + Gelismis Arama toggle | MVP | +2 gun | F4-S2 revize
2 | B-021§1 | P004 QwenListener intent + refinement | BEKLIYOR | intent_classify + generate_refinement_question | MVP | +1 gun | ~150 LOC ek
3 | B-021§1 | Chat UI (mesaj baloncuklari + sonuc listesi) | BEKLIYOR | /search sayfasi frontend revize | MVP | +2 gun | SearchPending carousel KORUNUR
PROJE BAZLI WORKSPACE
4 | DM-018 | projects tablosu (DB migration) | BEKLIYOR | id, user_id, name, status, timestamps | MVP | +0.5 gun | Migration 0009 veya ayri
5 | DM-018 | Mevcut tablolara project_id FK | BEKLIYOR | search_history, reading_list, chat_history | MVP | +0.5 gun
6 | DM-018 | Sidebar proje listesi + routing | BEKLIYOR | /projects/:id/search vs /search | MVP | +2 gun | Breadcrumb Projects > ProjeAdi
7 | DM-021 | r-ESTRA profil GLOBAL (project_id YOK) | ONAYLANDI | Tum projelerden ogrenir, projeler arasi tasinir | MVP | - | Rakiplerde YOK
KARAR HAFIZASI (project_decisions)
8 | DM-019 | project_decisions tablosu | BEKLIYOR | accept/reject/bookmark/note/method_select/topic_narrow/expand/direction_set | MVP | +1 gun | Migration ile birlikte
9 | DM-019 | Reject + reason -> r-ESTRA sinyal | BEKLIYOR | "konu disi"/"eski"/"zayif metodoloji" ogrenir | MVP | +0.5 gun | Rakiplerde YOK
10 | DM-019 | Karar UI (accept/reject butonlari + not) | BEKLIYOR | PaperCard action butonlari revize | MVP | +1 gun
IKI URUN HATTI (DM-020)
11 | DM-020 | Hat 1: Core PaperMind (proje bazli) | ONAYLANDI | Yayin hazirlama + danismanlik + literatur | MVP | - | Ana urun
12 | DM-020 | Hat 2: Savunma Simulasyonu | BEKLIYOR | Tez savunma provasi (juri sorulari + zayif nokta) | Post-MVP | Ayri sprint | Ayri satis / oturum basi
13 | DM-020 | Hat 2: Hakemlik Simulasyonu | BEKLIYOR | Hakem raporu (R1/R2) + revizyon onerileri + ret riski | Post-MVP | Ayri sprint | Ayri satis / oturum basi
IKI KATMANLI TIER FIYATLAMA
14 | B-021§5 | Katman 1: Proje sayisi (Free 2 / Pro sinirsiz) | TASARIM | Dogal upgrade tetikleyicisi | Post-MVP | - | Pricing page MVP olabilir
15 | B-021§5 | Katman 2: Icerik (Free: ara+top5 / Pro: +sohbet+ozet+liste+karar) | TASARIM | Ozellik kilidi ile deger | Post-MVP | -
16 | B-021§5 | Hat 2 Simulasyon: Oturum basi veya Pro+ dahil | TASARIM | Yuksek deger, yuksek fiyat | Post-MVP | -
TASARIM TWEAKS (Council 34)
17 | B-021§6 | Accent renk canlilaştirma degerlendirmesi | BEKLIYOR | amber-700 -> indigo-600 veya teal-600 (tek token) | MVP | ~2 saat | Pilot A/B icin hazirlik
18 | B-021§6 | Buton radius 6px -> 10px (radius-md) | BEKLIYOR | globals.css --radius-sm token swap | MVP | ~1 saat | Tek token degisikligi
19 | B-021§6 | Lora serif KORU (marka imzasi) | ONAYLANDI | Rakiplerde serif yok = diferansiyel avantaj | - | - | DEGISTIRME
20 | B-021§6 | Kok palet degisikligi | ERTELENDI | Pilot A/B test sonrasi karar | Post-MVP | - | F4-S1.5 WCAG AAA israf olmasin
RAKIP KARSILASTIRMA OZETI
21 | - | SciSpace: Chat-first + 12 arac sidebar | REFERANS | Swiss-army-knife, cok arac, cognitive overload | - | - | Biz 5 ekran sade
22 | - | Consensus: Search-first + Corpus/Deep toggle | REFERANS | Temiz minimal, kisisellesme YOK | - | - | Biz r-ESTRA ile fark
23 | - | Elicit: Agent-first + Suggested prompts | REFERANS | En temiz UI, systematic review kilitli | - | - | Biz evidence-first
24 | - | Undermind: Project + Search Architect + Report Writer | REFERANS | Proje bazli ama profil YOK, her projede sifirdan | - | - | Biz global profil + karar hafizasi
HAT 2 GENISLEME — SIMULASYON + EGITIM (Post-MVP)
25 | DM-020 | Danisma Egitimi (tam metin bazli) | BEKLIYOR | Geri bildirim ornekleri + yonlendirme senaryolari | Post-MVP S2 | Ayri sprint | works_clean_v2 kullanir
26 | DM-020 | Hakem Egitimi (tam metin bazli) | BEKLIYOR | Hakem raporu yazma rehberi + ornek inceleme | Post-MVP S2 | Ayri sprint | works_clean_v2 kullanir
27 | DM-020 | Editor Egitimi (tam metin bazli) | BEKLIYOR | Karar verme senaryolari + hakem atama mantigi | Post-MVP S3 | Ayri sprint | works_clean_v2 kullanir
AKILLI YONLENDIRME SISTEMI (MVP icinde)
28 | B-021§6 | AI ile Tartis prompt uretici | BEKLIYOR | Makale + proje baglami -> tartisma prompt (Claude/ChatGPT/Gemini uyumlu) | MVP | +0.5 gun | PaperCard "Daha Fazla" menu
29 | B-021§6 | Google Akademik arama linki | BEKLIYOR | Baslik+yazar -> scholar.google.com otomatik link | MVP | +0.5 gun | PaperCard metadata otomatik
30 | B-021§6 | Dergi platformu / DOI link | BEKLIYOR | DOI -> doi.org + yayinci sayfasi direkt link | MVP | +0.5 gun | Elsevier/Springer/Wiley...
31 | B-021§6 | Open Access versiyonu ara (Unpaywall) | BEKLIYOR | DOI -> Unpaywall API -> ucretsiz PDF linki | MVP | +0.5 gun | Akademisyen icin cok degerli
32 | B-021§6 | Atif Kopyala (APA/Chicago/Harvard) | BEKLIYOR | Metadata -> formatli atif -> clipboard | MVP | +0.5 gun | En cok istenen ozellik
33 | B-021§6 | Benzer Makaleler (ESTRA komsuluk) | BEKLIYOR | bibcoupling_top50 + ESTRA -> benzer liste | MVP | +1 gun | Faz 3 bibcoupling tablosu gerekli
B-022 | 2026-05-10 | Auth: Clerk (Supabase Auth SUPERSEDED) | Clerk @clerk/nextjs frontend + JWT verify backend; Supabase RLS Clerk JWT'yi kabul eder (custom JWT template) | Supabase Auth (SUPABASE_JWKS_URL .env.example:25 — kuru, JWT verify implementi yok) | Clerk: dev experience hızlı, social login + magic link + webhook hazır; Supabase Auth kuru kaldı, vakit kazandırır | Clerk webhook → Supabase user_profiles upsert (user.created/updated/deleted); 3-tier (0012) korunur, ENUM Supabase'de | AKTIF

## Genel Is Plani
# | Faz | Is Paketi | Durum | Aciklama | Tahmini Sure | Baslangic | Not
TAMAMLANAN FAZLAR
1 | F0 | Hazirlik (klasor + skeleton) | TAMAMLANDI | CLAUDE.md + DM_RULES + STATE + docs yapisi | 1 gun | 2026-04-29
2 | Hat A | Papermind_V2 Warehouse Closure | TAMAMLANDI | 10 manifest A-evidence, 24.87M paper corpus | 2 gun | 2026-04-28
3 | F1' | Master Plan + 5 mini-plan + 2 spec | TAMAMLANDI | B-001 560+ satir + F3a-e + F4-F7 + faithfulness + celery | 2 gun | 2026-04-29 | 11 plan dosyasi
4 | F2-D1 | Backend Day 1 (P000-P010) | TAMAMLANDI | FastAPI + 5-katman ABC + PMID Anchor + /api/search + 66/66 test | 1 gun | 2026-04-30 | B-014, 8 commit lokal
5 | F4-S1 | Frontend Shell (P037-P044) | TAMAMLANDI | Next.js 16 + Tailwind 4 + 8 ekran route + API client + Suspense | 1 gun | 2026-04-30 | 7 commit lokal
6 | F4-S1.5 | Design System Polish | TAMAMLANDI | shadcn init + 8-anatomi token + WCAG AAA palet + Defne persona | 1 gun | 2026-05-01 | B-020, 4 wrap commit
6b | F4-S2 | Demo Viz Cards + Design Pages | TAMAMLANDI | D25 NetworkMap (D3 force) + D27 GapHeatmap (SVG) + D29 JourneyProgress + D2 ColorTokens + DataVizCardFrame + route group refactor | 1 gun | 2026-05-01 | 79 dosya, 18.4K LOC, demo data (backend baglantisi yok)
SUPABASE ISLEMLERI
7 | Supa | B-002 Schema v1 | TAMAMLANDI | 12 tablo DDL + RLS + trigger + enum | <1 gun | 2026-04-29
8 | Supa | B-003 Static facts | TAMAMLANDI | 562K satir (theme + gap + method) | <1 gun | 2026-04-29
9 | Supa | B-008 Faz 1 PaperCard + GhostCard | TAMAMLANDI | 24.86M + 31.85M = ~28 GB | ~2 saat | 2026-04-30 | 2XL compute
10 | Supa | B-013 Faz 2 Satellite (3 tablo) | BEKLIYOR | sentence_role + d_estra + ref_age | ~1.5 saat | - | 4XL compute HAZIR
11 | Supa | Faz 3 Warehouse Mirror (12 tablo) | BEKLIYOR | quality + w_estra + velocity + field + ... + author | ~8 saat | - | 4 migration + notebook
12
PINECONE ISLEMLERI
13 | Pine | B-011 Bulk import (24.87M vector) | TAMAMLANDI | papers-bgem3 index, 1024-d cosine, eu-west-1 | ~3 saat | 2026-04-30
14
DEVAM EDEN / BEKLEYEN FAZLAR
15 | F4-S2 | Makale Ara wiring + shadcn import | DEVAM EDIYOR | P058 SearchPending + B42-039 nav refactor + D25/D27/D29 viz cards + D2 tokens | 3-4 gun | 2026-05-01 | 3D carousel + 4 viz card tamam, backend baglantisi BEKLIYOR
16 | F2-D2 | Backend Day 2-4 (P004-P009) | TAMAMLANDI | P004 Listener + P006 HybridPoolRouter + P007 Reranker + P008 Curator + P009 Presenter + Supabase lookup + P011-P015 resilience hardening (with_timeout/with_retry/Pinecone async wrapper/Supabase async helper/search route 503-504 mapping + 4 runbook iskelet) + 156/156 test PASS (145 unit + 11 integration) | 2-3 gun | 2026-05-01 | B-018 + Council 39 Supabase lookup + DM-030..034 + KD-36..40 (P011-P015 closure)
17 | F3 | Backend kalan 4 endpoint | ISKELET TAMAM | chat + summarize + enrich + reading-list + top5 + onboarding — 6 route placeholder veriyle calisiyor (501 degil) | 4-5 gun | - | Gercek LLM/OpenAlex entegre Faz 3
18 | F4-S3 | Sohbet + Liste ekranlari | BEKLIYOR | Chat SSE + reading list CRUD | 3-4 gun | -
19 | F4-S4 | Detay + Onboarding ekranlari | BEKLIYOR | Paper detail + onboarding wizard | 3-4 gun | -
20 | F4-S5 | Profil + Home + polish | BEKLIYOR | Mobile drawer + final polish | 2-3 gun | -
21 | F5 | Onboarding + Chat + Top5 + i18n | BEKLIYOR | P044-P052, ~1290 LOC | 4-5 gun | -
22 | F6 | Detay + Summarize + Ghost | BEKLIYOR | P053-P061, ~1200 LOC | 4-5 gun | -
23
HF INFERENCE ENDPOINT
24 | HF | Qwen2.5-7B-Instruct-AWQ endpoint | TAMAMLANDI | papermind-qwen, T4 GPU, eu-west-1, $0.50/h, scale-to-zero | - | 2026-04-30
25
BEKLEYEN KARARLAR (OPEN)
26 | OPEN | OPEN-005 Top 5 onay margin esigi | BEKLIYOR | Default 0.7 ile baslanir | - | - | F5 oncesi
27 | OPEN | OPEN-006 Ghost cache TTL | BEKLIYOR | 7d (master) vs 90d (DM-006 L1) | - | - | F3d oncesi
28 | OPEN | OPEN-007 Pilot 5 user listesi | BEKLIYOR | 5 user kim? | - | - | F7 oncesi
29 | OPEN | Lexical havuz karari | BEKLIYOR | FTS vs Pinecone sparse vs 2-havuz mock | - | - | F2 Day 2
30
PIVOT KARARLARI (B-021, 2026-05-01)
31 | PIVOT | Chat-first hybrid (/search revize) | ONAYLANDI | Chat default + gelismis keyword toggle (DM-017) | +2 gun | - | F4-S2 revize
32 | PIVOT | Proje bazli workspace (DB+routing) | ONAYLANDI | projects tablosu + FK + sidebar (DM-018) | +3 gun | - | F4-S3 veya ayri sprint
33 | PIVOT | Karar hafizasi (project_decisions) | ONAYLANDI | accept/reject/bookmark/note + r-ESTRA sinyal (DM-019) | +1 gun | - | Reject ogrenmesi
34 | PIVOT | r-ESTRA profil GLOBAL | ONAYLANDI | project_id FK almaz, tum projelerden ogrenir (DM-021) | - | - | Piyasada yok
35 | PIVOT | Hat 2: Simulasyon (savunma+hakemlik) | BEKLIYOR | Proje harici, ayri satis (DM-020) | Ayri sprint | - | Post-MVP
36 | PIVOT | Iki katmanli tier tasarimi | BEKLIYOR | Proje sayisi + icerik derinligi | - | - | Post-MVP uygulama
37 | PIVOT | Tasarim tweaks (accent+radius+Lora) | BEKLIYOR | Accent canli + radius 10px + Lora KORU | ~0.5 gun | - | MVP kucuk tweak
44 | F4 | B42-051 Design System Tokens | TAMAMLANDI | 4-zone CSS variables + Crimson Pro + Geist Mono fonts + zone.ts utility + globals.css zone overrides | <1 gun | 2026-05-01 | 5 zone x 2 mode = 10 palet seti
6c | F4-S3 | Hizli Tarama + Komponent Bati (D5/D6/D8/D9/D14/D15/D21/D29) | TAMAMLANDI | PaperCardLite + PaperCard GhostCard variant + AdvisorBanner zone-based + Sidebar D9 polish + CompassRoute pusula + StickyNoteButton + 404/500 editorial + JourneyProgress + brand canon orange #F97316 | 1 gun | 2026-05-01 | main branch ~14 commit (1fd5fbf..585cbd0); plan: docs/plans/F4_S3_hizli_tarama.md
6d | F4-S4 | Danisman ChatboxPanel (D16 canonical floating) | TAMAMLANDI | P073-P079 + 1 docs commit; 370x620 floating + slideIn 280ms + ESC + portal + Cmd+J + chat-fixture 4-reply round-robin; 29/29 vitest PASS | 1 gun | 2026-05-01 | B-023; main branch 8 commit; plan: F4_S4_advisor_chatbox.md
6e | F4-ad-hoc | P080 SimulationCurtain (D17 jüri perde animasyonu) | TAMAMLANDI | defense-5 sayfası açılış perdesi: 0s blackout → 0.7s curtain → 2.1s jury → 2.8s spotlight → 3.8s typewriter; sessionStorage pm_simulation_seen first-visit + prefers-reduced-motion final-state; 3/3 vitest PASS | <1 gun | 2026-05-01 | commit 72f7a09; B-NNN yok, page entegrasyonu Omer kararı
6f | F4-audit | Konsey 40 post-F4-S4 audit + 4 fix commit | TAMAMLANDI | (1) build kök neden url-state.ts orphan -> next build EXIT 1 (initial commit 93f75e7 artigi) (2) SimulationCurtain race fix runGenRef token (3) ChatboxPanel autofocus scope fix panelRef (4) DM_RULES R13.13 build PASS empirik kanit zorunlulugu | <1 gun | 2026-05-01 | commits 26d016d/9461d2e/d74586c/667f5a2; tsc + next build + 32/32 vitest + ESLint 26->23
6a | F4-Foundation | Brand canon + ui/button 4-variant + Sidebar D9 + Landing C3 + nav-config (12 commit) | TAMAMLANDI | Brand canon journey: amber -> indigo (78dd164) -> amber-700 (5e4cba2) -> orange #F97316 (d509e68/585cbd0 final). ui/button 4-variant (5f8e81c ritual/secondary/ghost/adviser) + lg padding fix (7f19e4f). Sidebar: D9 §5+§6 (3aba777) + logo+Wordmark üst blok (2f69da1) + state machine + workbench accent stripe (528db91). Landing: C3 editorial polish (4da47f7) + Wordmark component (d509e68). nav-config: PageStatus tipi + Inceleme rename (4bad6b2). Lockfile sync (a32ba64). | <1 gun | 2026-05-01 | main branch 12 commit; F4-S3 öncesi temel; F4-S4 ChatboxPanel için zemin
6b-be | F2-D3-D4 | Backend Resilience Hardening (P011-P015) + GitHub repo push | TAMAMLANDI | P011 utils/resilience.py (with_timeout/with_retry/call_resilient PEP 695 generics) + P012 Pinecone async wrapper (asyncio.to_thread + lru_cache singleton + PineconeQueryError) + P013 Supabase async helper (postgrest_client_timeout=10 + supabase_call_async + SupabaseQueryError) + P015 search route 503/504 mapping (ResilienceTimeoutError -> 504, Pinecone/Supabase -> 503) + 4 runbook iskelet (pinecone_down/supabase_down/hf_endpoint_down/search_p95_breach). 145/145 unit + 11/11 integration PASS, ruff + mypy strict. P014 Circuit Breaker -> KD-36 F7 P065 erteleme. GitHub: clean reinit + 228 dosya commit 93f75e7 + remote https://github.com/ofrencber/PaperMind.git + push main. | 1 gun | 2026-05-01 | commits 93f75e7/0d2438f/9a085ec; DM-030..034 + KD-36..40; Council 39 alt-§ 39a/b/c/d + Sercan post-hoc kanit sutunu
FRONTEND PLANI (2026-05-10, post-pivot)
45 | A | Visual wow polish (Magic UI BorderBeam+BlurFade + motion-presets.ts + 1_vitrin POC) | BEKLIYOR | Magic UI components copy (registry yok, kaynak kod kopya) + motion-presets.ts ortak Variants + 1_vitrin sayfa POC; 0 yeni dep (motion+tw-animate-css kurulu) | 1-2 gun | - | Indigo-600 accent korunur; warmup; izole
46 | B-fe | F9 P096 frontend redesign (k=5→k=25 cluster grid + 7-tag picker) | BEKLIYOR | 2.2 konu_belirleme sayfasi: cluster grid 25 oneri + 7-tag picker; F9 P096 backend (anchor lock + cluster_expander + estra_scorer) tamamlandiktan sonra wiring | 1-2 gun | - | F9 P096 backend bagimli; brief: /tmp/F9_P096_executor_brief.md
47 | F13 | 14 alt-sprint frontend, 16 sayfa | BEKLIYOR | docs/plans/F13_sayfa_plani_v2_implementation.md S1→S14; 39 endpoint + 8 migration + 6 cron; ~7200 LOC; Q1-Q12 (Cohere/ElevenLabs/cron/PR strategy) onay sonrasi baslar | ~30 gun | - | Konsey toplanti + per-sprint manifest gerekli
48 | D | Bibliometric chart real data wiring (BibliometricSummaryPage.tsx) | BEKLIYOR | d3 vs Recharts karar + gercek veri baglantisi; F13-S2 (Bibliometric Summary sayfasi) icinde ele alinir | F13-S2 dahil | - | d3 7.9 kurulu; Recharts alternatif

## Disk Hesabi
Faz | Tablo Grubu | Tahmini Disk (GB) | Kumulatif (GB) | Not
Faz 0 | Schema + static facts | 0.5 | 0.5
Faz 1 | PaperCard + GhostCard | 28 | 28.5 | 10 + 18 GB
Faz 2 | sentence_role + d_estra + ref_age | 3.5 | 32 | ~1.5 + 1.5 + 0.5
Faz 3a | 0005: quality_v3 + w_estra + velocity | 5.5 | 37.5 | ESTRA cekirdek
Faz 3b | 0006: field + interdisc + topic + metod + repl | 3.8 | 41.3 | Metadata + gate
Faz 3c | 0007: method_topic_affinity + centrality | 2.1 | 43.4 | Advisor
Faz 3d | 0008: bibcoupling_top50 + dim_author | 12 | 55.4 | En buyuk grup
| INDEX OVERHEAD (~20%) | 8 | 63.4 | Postgres index + toast
| TOPLAM |  | 63.4 | 80 GB disk hedefin %79 doluluk

## Bilinen Borclar
KD # | Borc | Kaynak | Yer / Cozum | Oncelik
KD-1 | F3a P010 vs F3b P010 numara cakismasi | B-010 | F3 sprint oncesi ayristir | Orta
KD-2 | Sentry init runtime path test | Council 23 | F7 P065 | Dusuk
KD-3 | PmidAnchor in-memory -> Supabase join | Council 23 | P005-followup | Orta
KD-4 | Auth middleware JWKS prod (ES256) | Council 23 | P002+ ayri slice | Yuksek
KD-6 | Listener+Anchor asyncio.gather paralel | Council 24 | F2 P004 sonrasi | Orta
KD-7 | signals_13 tam 13 sinyal listesi | Council 24 | P008 Curator concrete | Yuksek
KD-9 | Tier-aware rate limit | Council 24 | F5 onboarding sonrasi | Dusuk
KD-12 | MiniCheck NLI + ALCE recall impl | Council 25 | F2 P008 + Sercan | Yuksek
KD-13 | Reranker BGE -> Jina/Cohere A/B | Council 25 | Faz 2 post-MVP | Dusuk
KD-22 | Dark mode + chart tokens | Council 31 | Post-MVP | Dusuk
KD-23 | Tier-1 community 10 atom shadcn import | Council 31 | F4-S2 baslangic | Yuksek
KD-24 | SearchPending 3D carousel wiring | Omer+Defne | F4-S2 P058 TAMAM | TAMAMLANDI
KD-26 | Dark overlay dropdown menu | Omer+Defne | F5/F6 | Orta
KD-27 | Kutuphaneci chat refinement | Omer | Faz 2 post-MVP | Dusuk
KD-28 | Gelismis arama (faceted advanced) | Omer | Faz 2 post-MVP | Dusuk
KD-29 | Title/abstract OpenAlex lazy-fill (papers tablosu bos) | Council 39 | Faz 2: OpenAlex API batch lookup veya papers tablosu bulk fill | Yuksek
KD-30 | Zone-spesifik 5x3 starter sorular (chatbox) | F4-S4 Defne | F5+: STARTERS sabit liste -> page context-aware | Dusuk
KD-31 | Multi-thread persisted history (chatbox) | F4-S4 Defne | F5+: localStorage thread persistence + thread switcher | Dusuk
KD-32 | Focus-trap react-aria (chatbox modal a11y) | F4-S4 Defne | F5+: Tab/Shift+Tab boundary + ESC restore focus | Orta
KD-33 | Markdown render + Shiki syntax highlight (chat bubble) | F4-S4 Defne | F5+: react-markdown + remark-gfm + Shiki light theme | Dusuk
KD-34 | R13.13 build PASS empirik kanit gate (CI) | Konsey 40 | F7 P065 Sentry oncesi: GitHub Actions next build exit 0 zorunlu | Yuksek

## Frontend Sayfa Plani
# | Bolum | Sayfa | Slug | Komponent | Backend Endpoint | LLM Call | Engine / Servis Bagi | Migration Bagi | Auth | Tech | Durum | Plan | Faz | Sure
MARKETING + ENTRY
1 | Marketing | Landing | /landing | app/(marketing)/landing/page.tsx | - | - | - | - | Public | Statik + Wordmark | LIVE | BorderBeam hero CTA + BlurFade | A | 0.5 gun
2 | Marketing | Demo | /demo | app/(marketing)/demo/page.tsx | - | - | - | - | Public | Statik tanitim | LIVE | BlurFade reveal | A | 0.3 gun
3 | Entry | Dashboard | /(app) | app/(app)/page.tsx | GET /api/project (placeholder) | - | project_service | 0015 | Login | Card grid | BAGLANTI EKSIK | Proje listesi gercek + son aktivite | F13-S13 sonra | 0.5 gun
VITRIN + UYGULAMA
4 | Vitrin | Hizli Inceleme (Q) | /q | app/(app)/q/page.tsx | POST /api/q + /q/literature-review | Gemini Flash | listener+pool+rerank+curator+presenter | 0001-0008 | Public | motion + 3-stage Q1/Q3 | LIVE | V1-S15 P001+ UX polish | V1-S15 | V1 takip
5 | Uygulama | Makale Ara | /search | app/(app)/search/page.tsx | POST /api/search | Gemini Flash | pool_router + reranker + curator | 0001-0008 | Public | Hybrid + chat-first toggle | LIVE | Stabil | - | Stabil
6 | Uygulama | Sohbet | /chat | app/(app)/chat/page.tsx | POST /api/chat (SSE) | Gemini Flash | llm_service | 0015 | Login | SSE stream | BAGLANTI EKSIK | F4-S3 SSE wiring | F4-S3 | 3-4 gun
7 | Uygulama | Kutuphanem | /reading-list | app/(app)/reading-list/page.tsx | GET/POST/PATCH/DELETE /api/reading-list | - | reading_list service (inline) | 0015 | Login | Liste + CRUD | LIVE | UX polish | F4-S3 | 1 gun
8 | Uygulama | Onboarding | /onboarding | app/(app)/onboarding/page.tsx | POST /api/onboarding | - | dim service | 0011-0014 | Login | Wizard + form | LIVE | Profil tamamlama | F4-S4 | 2 gun
PROJE — KESIF (5 sayfa)
9 | Discovery | 2.1 Arastirma Alani | /project/{id}/discovery-1 | ResearchAreaConfirmPage.tsx | POST /api/research-area/messages + /anchor-candidates | Gemini Flash | anchor_finder + topic_exploration | 0015,0016 | Login | Chat + onaylama | LIVE | F13-S12 reset endpoint + 0022 | F13-S12 | 2 gun
10 | Discovery | 2.2 Konu Belirleme | /project/{id}/discovery-2 | TopicSuggestionPage.tsx | POST /api/top5 + /api/project | Gemini Flash | anchor + estra (planli) | 0016,0019 | Login | Top5 grid k=5 -> k=25 | LIVE | F9 P096: cluster_expander + 7-tag picker | B + B-fe | 1-2 gun FE
11 | Discovery | 2.3 Bibliyometrik | /project/{id}/discovery-3 | BibliometricSummaryPage.tsx | POST /api/project/{id}/bibliometrics | - | bibliometric_service + openalex | 0019 | Login | motion Variants + provenance | LIVE | D: chart real data (d3 vs Recharts) | D | 1-2 gun
12 | Discovery | 2.4 Tematik Analiz | /project/{id}/discovery-4 | ThematicAnalysisPage.tsx | GET /api/gap-heatmap (top=30) | - | gap_heatmap role + d3 | 0007,0008 | Login | d3 heatmap | LIVE | Stabil | - | Stabil
PROJE — INCELEME (5 sayfa)
15
16 | Curation | 3.3 Yontem & Veri | /project/{id}/curation-3 | MethodDataEthicsPage.tsx | POST /api/search (proxy) | Gemini Flash | pool_router proxy | 0001-0008 | Login | Liste + filtre | BAGLANTI EKSIK | F13 SCOPE-fix: RTF eslemesi karar | F13-S12 oncesi | 1+2 gun
17 | Curation | 3.4 Literatur Sentezi | /project/{id}/curation-4 | LiteratureSummaryPage.tsx | POST /api/summarize | Gemini Flash | curator + presenter | 0001 | Login | Markdown render | LIVE | F13-S11: synthesize endpoint | F13-S11 | ~2 gun
18 | Curation | 3.5 Genis Sentez | /project/{id}/curation-5 | ExtendedSummaryPage.tsx | POST /api/summarize | Gemini Pro | curator + presenter | 0001 | Login | Markdown uzun form | LIVE | Stabil | - | Stabil
PROJE — LITERATUR BOSLUGU (5 sayfa)
19 | GapAtlas | 4.1 Bosluk Haritasi | /project/{id}/gapatlas-1 | GapHeatmapCard.tsx | GET /api/gap-heatmap (14x18) | - | gap_heatmap role + d3 | 0007,0008 | Login | d3 heatmap | LIVE | F13-S12: 0023 calibration | F13-S12 | ~2 gun
20
23 | GapAtlas | 4.5 Akademik Etki | /project/{id}/gapatlas-5 | SocialPulsePage.tsx | POST /api/search (proxy) | - | impact-curve (planli) | - | Login | Trend chart planli | BAGLANTI EKSIK | F13-S11: /api/workshop/impact-curve | F13-S11 | ~2 gun
PROJE — YAZIM & HAZIRLIK (4 sayfa)
26 | Authoring | 5.3 Akademik Dil | /project/{id}/authoring-3 | AcademicLanguagePage.tsx | POST /api/chat (proxy) | Gemini Flash | style/{tr,en,id}.json (planli) | 0026 | Login | Chat tabanli | BAGLANTI EKSIK | F13-S3: paraphrase + style/ | F13-S3 | ~3 gun
PROJE — SAVUNMA (6 sayfa)
30 | Defense | 6.3 Bireysel Kontrol | /project/{id}/defense-3 | IndividualFeedbackPage.tsx | POST /api/chat (proxy) | Gemini Flash | checklist/{makale,tez}_{tr,en}.json | - | Login | Chat tabanli | BAGLANTI EKSIK | F13-S8: 3 endpoint | F13-S8 | ~3 gun
32
PROJE — ARACLAR (2 sayfa)
34 | Tools | S1 Arastirma Defteri | /project/{id}/notebook | NotebookPage.tsx | POST /api/diary/event + GET /timeline + PATCH + /pre-advisor-summary | Gemini Flash | diary_service + diary_pre_advisor | 0029 | Login | Liste + CRUD -> DiarySidebar | BAGLANTI EKSIK | F13-S1: refactor -> DiarySidebar (4 endpoint var) | F13-S1 | ~2 gun (FE refactor)

## Servis & Engine Katmani
# | Katman | Dosya | Sorumluluk | Cagiran Endpoint | Dis Bagimlilik | Durum | Faz
MEVCUT — api/services/ (15 dosya)
1 | service | llm_service.py | Gemini wrapper, fence strip, max_tokens override | /api/chat, /api/summarize, +many | Gemini API | LIVE | F8
2 | service | litellm_router.py | 3-dil routing (PRESENTER_TR/EN/ID_MODEL) | presenter dolayli | LiteLLM | LIVE | F8
3 | service | elevenlabs_tts.py | Text-to-speech vitrin Q3 | /api/tts | ElevenLabs | LIVE | F8
4 | service | bibliometric_service.py | OpenAlex bibliometrics + connected papers | /api/project/{id}/bibliometrics, /api/connected-papers | OpenAlex+Supabase | LIVE | F3
5 | service | openalex_polite.py | OpenAlex polite pool (.edu.tr email) | bibliometric, enrich, impact-curve | OpenAlex | LIVE | F3
6 | service | faithfulness_gate.py | Curator faithfulness threshold (config/) | curator | - | LIVE | F2-D2
7 | service | anchor_finder.py | Anchor lock + research-area top-K | /api/research-area/* | Pinecone+Supabase | LIVE | F2-D2
8 | service | anchor.py | ? duplicate / yardimci | - | - | LIVE | ?
9 | service | listener.py | Q ilk katman: query parse + intent | /api/q | - | LIVE | F2-D1
10 | service | pool_router.py | Hybrid pool routing (dense + sparse) | /api/q, /api/search | Pinecone | LIVE | F2-D2
11 | service | reranker.py | BGE-v2-m3 local rerank | /api/q, /api/search, /api/top5 | HF model local | LIVE | F2-D2
12 | service | curator.py | Faithfulness + de-dup + ranking | /api/q, /api/search, /api/top5, /api/summarize | - | LIVE | F2-D2
13 | service | presenter.py | Final formatting + 3-dil routing | /api/q, /api/search, /api/summarize | litellm_router | LIVE | F2-D2
14 | service | translator.py | Query translate (TR/EN) | translate_query | LiteLLM | LIVE | F8
15 | service | diary_service.py | Diary CRUD (Supabase) | /api/diary/* | Supabase | LIVE | F13-S1
MEVCUT — api/services/role_modules/ (8 dosya)
16 | role | librarian.py | Q3 literature librarian persona | /api/q/literature-review | - | LIVE | F2
17 | role | vitrin_literature.py | Vitrin Q3 literature compose | /api/q/literature-review | llm_service | LIVE | F2
18 | role | vitrin_summary.py | Vitrin Q1 summary compose | /api/q | llm_service | LIVE | F2
19 | role | topic_exploration.py | 2.1 anchor exploration | /api/research-area/messages | llm_service | LIVE | PIVOT
20 | role | translate_query.py | Multilingual query route | /api/search dolayli | translator | LIVE | F8
21 | role | method_selection.py | Method-specific retrieval | ? (kullanici belli degil) | - | LIVE | ?
22 | role | gap_heatmap.py | Gap matrix compute | /api/gap-heatmap | Supabase | LIVE | F3
23 | role | diary_pre_advisor.py | Diary pre-advisor LLM summary (Flash 2K) | /api/diary/pre-advisor-summary | llm_service | LIVE | F13-S1
PLANLI — engine/ (~30 dosya, klasor henuz yok)
24 | engine | engine/style/{tr,en,id}.json | Akademik dil/uslup sozlugu (3 dil) | /api/workshop/paraphrase | - | PLANLI | F13-S3
25 | engine | engine/checklist/makale_tr.json | Makale kontrol listesi TR | /api/workshop/manuscript/coherence-check | - | PLANLI | F13-S8
26 | engine | engine/checklist/makale_en.json | Makale kontrol listesi EN | /api/workshop/manuscript/coherence-check | - | PLANLI | F13-S8
27 | engine | engine/checklist/tez_tr.json | Tez kontrol listesi TR | /api/workshop/manuscript/coherence-check | - | PLANLI | F13-S8
28 | engine | engine/checklist/tez_en.json | Tez kontrol listesi EN | /api/workshop/manuscript/coherence-check | - | PLANLI | F13-S8
29 | engine | engine/citation/apa.py | APA atif format | /api/workshop/citation-* | - | PLANLI | F13-S4
30 | engine | engine/citation/vancouver.py | Vancouver atif format | /api/workshop/citation-* | - | PLANLI | F13-S4
31 | engine | engine/citation/ieee.py | IEEE atif format | /api/workshop/citation-* | - | PLANLI | F13-S4
32 | engine | engine/citation/chicago.py | Chicago atif format | /api/workshop/citation-* | - | PLANLI | F13-S4
33 | engine | engine/citation/mla.py | MLA atif format | /api/workshop/citation-* | - | PLANLI | F13-S4
34 | engine | engine/dictionary/{tr,en,id}.json | 3-dil terim sozlugu | citation-translate | - | PLANLI | F13-S4
35 | engine | engine/personas/journal/* | Hakem (3 persona) prompt + persona JSON | /api/defense/reviewer-3persona | - | PLANLI | F13-S9
36 | engine | engine/personas/jury/* | Juri (5 persona) prompt + persona JSON | /api/defense/jury-question | - | PLANLI | F13-S10
37 | engine | engine/journals/review_distribution.json | Dergi review threshold dagilimi | journal-suggest, journal-calibration | - | PLANLI | F13-S8/S9
38 | engine | engine/statcheck/multilingual.json | Statistik kontrol heuristik (3-dil) | /api/defense/statcheck | - | PLANLI | F13-S9
39 | engine | engine/jury/reaction_thresholds.json | Juri reaction skor esikleri (Cohen kappa hedef >=0.7) | /api/defense/answer-score, jury-decision-band | - | PLANLI | F13-S10
40 | engine | engine/completion/badge_thresholds.json | Rozet esikleri | /api/completion/snapshot | - | PLANLI | F13-S13
41 | engine | engine/completion/oneri_kurali.json | Oneri kurali (sonraki adim) | /api/completion/snapshot | - | PLANLI | F13-S13
42 | engine | engine/completion/calculator.py | Tamamlama yuzde hesabi | /api/completion/snapshot | - | PLANLI | F13-S13
43 | engine | engine/completion/prompts/* | Tamamlama feedback prompts | /api/feedback/project-completion | - | PLANLI | F13-S13

## Migration Sirasi
# | Migration | Tablo / Icerik | Satir Sayisi | Disk | RLS | Apply Tarih | Bagli Endpoint | Bagli Sayfa | Durum | Faz
APPLIED — Schema temel (F0-F2)
1 | 0001_init_schema_v1.sql | 12 tablo (chat,session,note...) | - | - | RLS | 2026-04-29 | /api/chat,/api/notes | dashboard,chat,notebook | APPLIED | F0
2 | 0002_static_facts.sql | theme + gap + method dim | 562K | <1GB | - | 2026-04-29 | /api/gap-heatmap | 2.4, 4.1 | APPLIED | F1
3 | 0003_paper_anchor_facts.sql | paper anchor facts | 24.86M | ~14GB | RLS | 2026-04-30 | /api/q,/api/search,/api/top5 | Q, search, 2.2 | APPLIED | F2
4 | 0004_paper_satellite_facts.sql | paper satellite (3 alt-tablo) | ? (sayilmadi) | ~14GB | RLS | - | /api/q | Q | APPLIED | F2
APPLIED — Faz 2/3 ESTRA + temporal
5 | 0005_paper_estra_temporal.sql | d_estra + ref_age | - | - | - | 2026-05-08 | /api/q | Q | APPLIED | F2
6 | 0006_paper_metadata.sql | interdisc + paper_topic + metod | - | - | - | 2026-05-08 | /api/search,/api/top5 | search, 2.2 | APPLIED | F2
7 | 0007_method_centrality.sql | centrality | - | - | - | 2026-05-08 | /api/gap-heatmap,/api/gap-profile | 2.4, 4.1, 4.2 | APPLIED | F2
8 | 0008_neighbor_bibcoupling.sql | bibcoupling 643M | 643M | ~30GB | - | 2026-05-08 | /api/connected-papers | 3.2 | APPLIED | F2
APPLIED — Onboarding & Profil (F3)
9 | 0011_create_dim_field.sql | dim_field | - | <1MB | - | - | /api/fields | onboarding | APPLIED | F3
10 | 0012_user_profile_fields_and_tier_refactor.sql | user_profiles + 3-tier ENUM | - | - | RLS | - | /api/onboarding | onboarding | APPLIED | F3
11 | 0013_create_dim_subfield.sql | dim_subfield | - | - | - | - | /api/subfields | onboarding | APPLIED | F3
12 | 0014_user_profile_subfields_bridge.sql | user_subfields bridge | - | - | RLS | - | /api/onboarding | onboarding | APPLIED | F3
APPLIED — Proje workspace (PIVOT)
13 | 0015_projects_skeleton.sql | projects + project_decisions | - | - | RLS | - | /api/project,/api/chat,/api/notes,/api/reading-list | dashboard,project,chat,notebook,reading-list | APPLIED | PIVOT
14 | 0016_project_cluster.sql | project_cluster (k=5 -> k=25 plan) | BEKLIYOR | - | RLS | - | /api/top5,/api/research-area/* | 2.1, 2.2 | APPLIED | PIVOT
15 | 0017_waitlist_table.sql | waitlist | - | <1MB | - | - | /api/waitlist | landing | APPLIED | F3
APPLIED — Proje seed + concept
16 | 0019_project_seed_papers.sql | project_seed_papers | - | - | RLS | - | /api/project/{id}/bibliometrics | 2.3 | APPLIED | F3
17 | 0021_concept_term_arm.sql | concept_term_arm (2.5 kavram agi) | - | - | RLS | 2026-05-09 | ? (yok) | 2.5 | APPLIED | F4-S2
APPLIED — F13-S1 (yeni)
18 | 0029_project_event.sql | project_event (id,proj_id,user_id,page_slug,paper_id,event_type,payload,created_at,resolved_at) | - | - | RLS | 2026-05-10 | /api/diary/* | S1 notebook | APPLIED | F13-S1
PLANLI — F13
19 | 0022_extended_affinity.sql | extended_affinity (warehouse query) | ~30M | ? | RLS | - | ? (2.1 reset/affinity) | 2.1 | PLANLI | F13-S12
20 | 0023_gap_matrix_calibration.sql | gap_matrix_calibration | - | - | RLS | - | /api/gap-heatmap (calibrated) | 4.1 | PLANLI | F13-S12
21 | (0024 reddedildi) | user_profiles.metadata.gap_targets JSONB tercih | - | - | - | - | - | - | PLANLI | F13
22 | 0025_project_progress.sql | project_progress | - | - | RLS | - | /api/workshop/maturity,advisor-summary | 5.1 | PLANLI | F13-S2
23 | 0026_silent_learning.sql | silent_learning (paraphrase decision log) | - | - | RLS | - | /api/workshop/paraphrase-decision | 5.3 | PLANLI | F13-S3
24 | 0027_manuscript_section.sql | manuscript_section | - | - | RLS | - | /api/workshop/manuscript/* | 6.1 | PLANLI | F13-S6
25 | 0028_defense_session.sql | defense_session | - | - | RLS | - | /api/workshop/defense/* | 6.2 | PLANLI | F13-S7
26 | 0030_completion.sql | completion (snapshot + feedback) | - | - | RLS | - | /api/completion/* | S2 | PLANLI | F13-S13

## Dis Servisler & Maliyet
# | Servis | Amac | ENV Key | Key Durumu | Kullanan Endpoint | Maliyet (tahmin) | Risk | Faz
1 | Supabase | Auth + DB + storage + RLS | SUPABASE_URL, SUPABASE_PUBLISHABLE_KEY, SUPABASE_SECRET_KEY, SUPABASE_JWKS_URL | VAR (canli) | Tum DB endpoint (~30) | Pro $25/ay | K-029 ISP block :6543; Session Pooler :5432 kullaniliyor | F0
2 | Pinecone | Vector retrieval (papers-bgem3 1024-d cosine) | PINECONE_API_KEY, PINECONE_INDEX_NAME (papers-bgem3), PINECONE_ENVIRONMENT (us-east-1) | VAR (canli) | /api/q, /api/search, /api/top5, /api/research-area/* | 24.87M vector ~$70/ay | F13-S10 jury-claims yeni namespace karari (Q6) | F2-D2
3 | Gemini | LLM (Flash + Pro) | GEMINI_API_KEY, GEMINI_FLASH_MODEL=2.5-flash, GEMINI_PRO_MODEL=2.5-pro | VAR (canli) | /api/q, /api/chat, /api/summarize, /api/top5, F13 ~30 endpoint | $10/ay@100proje (hedef); R6 paraphrase Pro $$ riski | F13-S3 Pro->Flash fallback (R6) | F8
4 | HuggingFace Endpoint | Qwen2.5-7B-Instruct-AWQ + BGE-v2-m3 local rerank | HF endpoint URL (kod ici) | VAR (canli) | /api/q (rerank), /api/search (rerank) | T4 GPU $0.50/h scale-to-zero | - | F2-D2
5 | OpenAlex | Bibliometrics + paper metadata | OPENALEX_EMAIL=dr.ofrencber@gaziantep.edu.tr (polite pool) | VAR | /api/project/{id}/bibliometrics, /api/connected-papers, /api/enrich, impact-curve | Free (.edu.tr polite) | - | F3
6 | Cohere rerank-3 | F13-S10 juri HyDE fanout rerank | COHERE_API_KEY | ? (Q1 cevapsiz) | /api/defense/hyde-fanout-rerank | ? (kullanim bagli) | R1: yoksa BGE fallback (kurulu) | F13-S10
7 | ElevenLabs | Text-to-speech (vitrin Q3) | ELEVENLABS_API_KEY | ? (Q2 cevapsiz) | /api/tts | 4. tier ucretli | R2: sadece vitrin disinda kullanim karari yok | F8
8 | Mail provider | S1 aylik digest + S2 kapanis mail | ? (Resend/SES/SendGrid) | ? (Q4 cevapsiz) | S1, S2 cron | ? (saglayiciya bagli) | Q4: hangisi secilecek karari yok | F13-S1, S13
9 | Cron platform | 6 cron job F13 | ? (Render/Supabase/GH Actions) | ? (Q3 cevapsiz) | F13-S14 | ? (platforma bagli) | Q3: hangi cron platform karari yok | F13-S14
10 | Redis | Cache + Celery broker | REDIS_URL=redis://localhost:6379/0 | VAR (lokal) | TTL: 30 gun ozet, 7 gun sentez | Lokal bedava; prod karar yok | Prod Upstash/Render Redis karari | F8

## Veri Akisi & Demo Path
# | Asama | Sayfa / Endpoint | Girdi | Islem (5-katman vb) | Cikti | DB Tablo | Sure (p95) | Durum
VITRIN — Q akisi (5-katman)
1 | 1. Listener | /q -> /api/q | user prompt (TR/EN/ID) | listener.py: query parse + intent | intent + parsed_query | - | ~50ms | LIVE
2 | 2. Pool Router | /api/q | parsed_query + embedding | pool_router.py: hybrid (dense Pinecone + sparse) | candidate paper IDs (~200) | paper_anchor_facts | ~300ms | LIVE
3 | 3. Reranker | /api/q | candidate IDs + query | reranker.py: BGE-v2-m3 local rerank | top-K (K=12 Q1, K=25 Q3) | - | ~400ms | LIVE
4 | 4. Curator | /api/q | top-K + faithfulness | curator.py: faithfulness gate + de-dup | curated K papers | - | ~100ms | LIVE
5 | 5. Presenter | /api/q | curated K + lang | presenter.py: 3-dil (litellm_router) + Gemini Flash | final response (~400 kelime Q1, 7-tag Q3) | - | ~1.5s | LIVE
PROJE YOLCULUGU — Discovery (2.x)
6 | 2.1 Arastirma Alani | /discovery-1 | paper_id + chat msg | anchor_finder + topic_exploration | anchor lock + 5 cluster | project_cluster, projects | ~2s | LIVE
7 | 2.2 Konu Belirleme | /discovery-2 | locked anchor | top5 -> (PLANLI: cluster_expander + estra_scorer k=25) | 5 -> 25 oneri + 7-tag | project_cluster | ~1.5s -> 3s | LIVE -> F9 P096
8 | 2.3 Bibliyometrik | /discovery-3 | project_id | bibliometric_service + openalex_polite | tablo + planli chart | project_seed_papers | ~3s | LIVE
9 | 2.4 Tematik | /discovery-4 | project_id | gap_heatmap role (top=30) | d3 heatmap | paper_metadata, method_centrality | ~1s | LIVE
PROJE YOLCULUGU — Curation (3.x)
11
12 | 3.2 Iliskili Cal | /curation-2 | paper_id | connected-papers (bibcoupling 643M) | network | neighbor_bibcoupling | ~2s | LIVE
13 | 3.3 Yontem & Veri | /curation-3 | project + filtre | search proxy (PLANLI: SCOPE-fix) | liste | paper_metadata | ~1.5s | BAGLANTI EKSIK
14 | 3.4 Sentez | /curation-4 | top papers | summarize (curator + presenter) | markdown | - | ~5s (Pro) | LIVE
15 | 3.5 Genis Sentez | /curation-5 | top papers | summarize (Pro uzun) | markdown uzun | - | ~15s (Pro) | LIVE
PROJE YOLCULUGU — GapAtlas (4.x)
16
17 | 4.2 Bosluk Profili | /gapatlas-2 | project | gap_profile | liste + skor | - | ~1s | LIVE
18 | 4.3 Ozgunluk | /gapatlas-3 | project + kavram | PLANLI: workshop/originality | skor + neden | - | - | PLANLI
19 | 4.4 Karsilastirma | /gapatlas-4 | 2 paper | PLANLI: workshop/compare | tablo | - | - | PLANLI
20 | 4.5 Etki Egrisi | /gapatlas-5 | paper_id | PLANLI: workshop/impact-curve (OpenAlex) | line chart | - | - | BAGLANTI EKSIK
PROJE YOLCULUGU — Authoring (5.x) PLANLI
21
22 | 5.2 Yayin Taslagi | /authoring-2 | tema + format | PLANLI: workshop/topic-proposals + draft-skeleton | IMRaD iskelet | - | - | PLANLI
23 | 5.3 Akademik Dil | /authoring-3 | metin | PLANLI: workshop/paraphrase + style/{tr,en,id}.json + 0026 | iyilestirilmis metin | silent_learning | - | BAGLANTI EKSIK
24 | 5.4 Atif Stil | /authoring-4 | referans + stil | PLANLI: 4 endpoint citation-* + 5 stil py + dictionary | format. atif | - | - | PLANLI
PROJE YOLCULUGU — Defense (6.x) PLANLI
25
26 | 6.2 Savunma Format | /defense-1 | project | PLANLI: defense/generate-questions + suggest-jury + 0028 | soru havuzu + juri | defense_session | - | PLANLI
27 | 6.3 Bireysel | /defense-3 | metin | PLANLI: 3 endpoint (journal/coherence/personal) + checklist/ | geri bildirim | - | - | BAGLANTI EKSIK
28 | 6.4 Dergi Sim | /defense-4 | metin + dergi | PLANLI: 3 endpoint + statcheck + journals + personas/journal/ | 3-persona hakem | - | - | PLANLI
29 | 6.5 Juri Sim | /defense-5 | metin | PLANLI: 5 endpoint + Cohere rerank + personas/jury/ + jury/ | 5-persona juri | - | - | BAGLANTI EKSIK
30 | S2 Tamamlama | /defense-6 | project | PLANLI: completion/snapshot + feedback + 0030 + badge JSON | rozet + ozet + mail | completion | - | PLANLI
YAN AKIS — Defter (S1)
31
32 | S1 timeline oku | /notebook (DiarySidebar) | project_id + cursor | diary_service.py timeline | liste | project_event | ~300ms | LIVE
33 | S1 pre-advisor | /notebook (sayfa) | event listesi | diary_pre_advisor.py + Gemini Flash 2K | ozet metin | project_event | ~3s | LIVE

## Backend Endpoints
# | B-ID (RENCBER) | Method | Path (canonical) | Path (mevcut kod) | Dosya:Satir | F-ID (FE) | Tablo / W-ID | Auth | Cache | DoD / Aciklama | LLM | Dis Servis | Durum | Faz | Kanit Kaynak | L1 Listener | L2 Anchor | L3 PoolRouter | L4 Reranker | L5 Curator | L6 Presenter
GRUP 1 — ARAMA & MAKALE METADATA (B-01..B-25)
1 | B-01 | POST | /api/search | /api/search | search.py:114 | F-04, F-05 | fact_paper_id_card (W-36) + Pinecone (W-28) + sentence (W-24) + quality (W-09) | public | Redis L1 90g | 5-katman Top10 + KararBant + LVR; p50<4s | Flash | Pinecone+Supabase | LIVE | F2-D2 | A: search.py:114 + B: RENCBER B-01 | ✓ | ✓ | ✓ | ✓ | ✓
2 | B-02 | GET | /api/papers/{paper_id} | /api/paper/{paper_id} | paper_detail.py:56 | F-06 | works_clean_v2 (W-01) + fact_paper_id_card (W-36) | public | edge 1h | PaperCard + null abstract fallback | - | Supabase+Pinecone | LIVE | F3 | A: paper_detail.py:56 + B-02 (path renamed: papers->paper)
6 | B-06 | GET | /api/papers/{id}/refs | /api/paper/{id}/export | paper_detail.py:109 | F-07 | fact_citation_edge (W-10) + works_clean_v2 | public | edge 1h | Pagination 50/sayfa; year/centrality sort | - | Supabase | LIVE | F3 | A: paper_detail.py:109 (export form) + B-06 partial
9 | B-09 | GET | /api/papers/{id}/bibcoupling | /api/connected-papers/{paper_id} | connected_papers.py:77 | F-08 | fact_paper_bibcoupling_top50 (W-14) | public | edge 24h | Top-50 komsu + cosine; MVP wow endpoint | - | Supabase | LIVE | F3 | A: connected_papers.py:77 + B-09 (path renamed)
23 | B-23 | GET | /api/gap-matrix | /api/gap-heatmap | gap_heatmap.py:181 | F-12 | fact_gap_matrix (W-27) | public | edge 24h | 11-boyut x tema heatmap | - | Supabase | LIVE | F3 | A: gap_heatmap.py:181 + B-23 (renamed)
25 | B-25 | GET | /api/health + /api/version | - | - | F-01 | manifest hash + Pinecone health | public | no-cache | 200 + version + warehouse hash | - | - | PLANLI | F3 | B: B-25 — main.py icinde health endpoint kontrolu
GRUP 2 — AUTH (B-26..B-30) — Supabase Auth client-side
28 | B-28 | GET | /api/auth/me | - | (JWT middleware) | - | dim_user + projects count | jwt | edge 60s | Profile + plan + kota | - | Supabase | PLANLI | F3 | B: B-28 — middleware mevcut, ayri endpoint yok
GRUP 3 — PROJE & TOPIC (B-31..B-37) — PIVOT genisletti
31 | B-31 | GET/POST | /api/projects | /api/project | project.py:187,290 | F-03 | fact_user_project (B-002) / projects | jwt | edge 60s | Liste + create; pagination 50/sayfa; project_lock | - | Supabase | LIVE | PIVOT | A: project.py:187 (POST), 290 (GET) + B-31 (renamed: projects->project)
32 | B-32 | GET/PATCH/DEL | /api/projects/{id} | /api/project/{id} | project.py:319 | F-03 | fact_user_project + project_papers | jwt+owner | edge 60s | Detay/guncelle/sil; soft-delete 30g | - | Supabase | LIVE (partial) | PIVOT | A: project.py:319 (GET only) + B-32 — PATCH/DELETE eksik
33 | B-33 | GET/POST/DEL | /api/projects/{id}/papers | - | - | F-03 | project_papers + works_clean_v2 | jwt+owner | edge 60s | Bookmark; bulk add; max 1000/proje | - | Supabase | PLANLI | F3 | B: B-33 — current proje yapisi project_seed_papers (0019)
34 | B-34 | GET/POST/DEL | /api/projects/{id}/topics | - | - | F-03 | project_topics + dim_theme | jwt+owner | edge 60s | Tema kilidi; topic_lock guardrails | - | Supabase | PLANLI | F3 | B: B-34 — project_cluster (0016) + concept_term_arm (0021) ile kismen ortusur
35 | B-35 | POST | /api/topic/suggest | /api/top5 + /api/research-area/anchor-candidates | top5.py:46 + research_area.py:84 | F-04 | dim_theme + Pinecone (W-28) + PMID hierarchy | jwt | edge 5min | Top-5 tema oneri + confidence | Flash | Pinecone+Supabase | LIVE | F2-D2 | A: top5.py:46 + research_area.py:84 (PIVOT-genisletti) + B-35
36 | B-36 | POST | /api/projects/{id}/topic-lock | /api/research-area/messages | research_area.py:55 | F-03 | project_topics + Pinecone metadata $in | jwt+owner | no-cache | HARD filter aktif; D/F/S set | Flash | Pinecone+Supabase | LIVE (partial) | PIVOT | A: research_area.py:55 (anchor lock) + B-36 (kismi)
37 | B-37 | POST | /api/projects/{id}/topic-unlock | - | - | F-03 | project_topics | jwt+owner | no-cache | Lock kaldir + audit log | - | Supabase | PLANLI (F13-S12) | F13-S12 | B: B-37 — F13-S12 /api/project/{id}/research-area/reset olarak planlandi
GRUP 4 — COVERAGE & SEARCH VARIANTS (B-38..B-42)
39 | B-39 | POST | /api/search/semantic | /api/search (semantic leg) | search.py:114 | F-04 | Pinecone (W-28) + BGE-M3 query encode | jwt | edge 5min | Pure dense; 4-katman; p50<2s | Flash | Pinecone | LIVE | F2-D2 | A: /api/search icinde dense leg; B-39 | ✓ | ✓ | ✓ | ✓ | ✓
40 | B-40 | POST | /api/search/hybrid | /api/search | search.py:114 | F-04 | Pinecone dense+sparse + BM25 fallback | jwt | edge 5min | Dense+sparse RRF k=60; topic_lock filter | Flash | Pinecone | LIVE | F2-D2 | A: /api/search hybrid pool_router + B-40 | ✓ | ✓ | ✓ | ✓ | ✓
GRUP 5 — NOTLAR & HIGHLIGHTS (B-43..B-46)
43 | B-43 | GET/POST | /api/notes | /api/notes | notes.py:30,40 | F-14 | fact_user_note (B-002) | jwt | edge 30s | Markdown; per-project + per-paper; 10K/user kota | - | Supabase | LIVE | F3 | A: notes.py:30,40 + B-43
44 | B-44 | GET/PATCH/DEL | /api/notes/{id} | /api/notes/{note_id} | notes.py:56,74 | F-14 | fact_user_note | jwt+owner | edge 30s | Detay/guncelle/sil; revision history son 10 | - | Supabase | LIVE (partial) | F3 | A: notes.py:56,74 (PATCH+DELETE; GET ayri yok) + B-44
45 | B-45 | POST | /api/notes/{id}/highlight | - | - | F-14 | fact_user_highlight + fact_paper_sentence (W-24) | jwt+owner | no-cache | Sentence-level; ALCE egitim verisi | - | Supabase | PLANLI | F6 | B: B-45 — sentence_role yuklendi (r09)
46 | B-46 | GET | /api/projects/{id}/notes | - | - | F-14 | fact_user_note + projects | jwt+owner | edge 60s | Proje altindaki tum notlar; tag filter | - | Supabase | PLANLI | F6 | B: B-46
GRUP 6 — DIS API (B-47..B-49)
49
GRUP 7 — DATASET & ETIK (B-50..B-53)
GRUP 8 — LLM ENDPOINTS (B-54..B-58)
54 | B-54 | POST | /api/llm/summarize | /api/summarize | summarize.py:88,117 | F-06 | fact_paper_sentence (W-24) + Qwen-7B (PIVOT: Gemini) | jwt | edge 24h | Per-paper ozet 100 kelime; 50/free 500/pro | Pro | - | LIVE | F3 | A: summarize.py:88 (POST 202) + 117 (GET task) + B-54 (LLM PIVOT Qwen->Gemini)
55 | B-55 | POST | /api/llm/explain | - | - | F-06 | fact_paper_abstract_flags + Gemini | jwt | edge 24h | Method/finding/limitation; sentence-level grounding | Flash | - | PLANLI | F6 | B: B-55
56 | B-56 | POST | /api/llm/critique | - | - | F-13 | paper + bibcoupling + cited authors | jwt | edge 24h | JuryMind ozelligi; sycophancy yasak | Pro | - | PLANLI (F13-S10) | F13-S10 | B: B-56 — F13-S10 /api/defense/jury-question olarak planlandi
57
58 | B-58 | GET | /api/llm/limit-status | - | - | F-02 | fact_user_quota | jwt | edge 30s | Kalan LLM cagri; reset; upgrade CTA | - | Supabase | PLANLI | F3 | B: B-58
GRUP 9 — RECOMMEND (B-59..B-63)
59 | B-59 | GET | /api/recommend/related | - | - | F-08 | bibcoupling + Pinecone HARD filter | jwt | edge 6h | HARD+rerank; topic_lock zorunlu | - | Pinecone+Supabase | PLANLI | F6 | B: B-59
60 | B-60 | GET | /api/recommend/diverse | - | - | F-08 | interdisc + ref_age | jwt | edge 6h | MMR diversity; alan-arasi disclaimer | - | Supabase | PLANLI | F6 | B: B-60
61 | B-61 | GET | /api/recommend/cross-domain-flag | - | - | F-08 | Pinecone metadata D/F/S + topic_lock | jwt | edge 6h | Dusuk confidence + D mismatch flag | - | Pinecone | PLANLI | F6 | B: B-61
62 | B-62 | GET | /api/recommend/confidence | - | - | F-08 | q_weak + v_conf + sim score | jwt | edge 6h | <0.4 dusuk; <0.2 ret | - | Supabase | PLANLI | F6 | B: B-62
63 | B-63 | POST | /api/recommend/explain | - | - | F-08 | recommendation trace + LLM | jwt | edge 1h | Niye onerildi? PMID + cite + sim aciklama | Flash | - | PLANLI | F7 | B: B-63
GRUP 10 — BIBLIO & EXPORT (B-64..B-70)
64 | B-64 | GET | /api/biblio/cite-as/{format} | - | - | F-06 | works_clean_v2 + dim_author + dim_journal | public | edge 24h | APA/MLA/Chicago/Vancouver; CSL backend | - | Supabase | PLANLI (F13-S4) | F13-S4 | B: B-64 — F13-S4 /api/workshop/citation-format ile ortusur
65 | B-65 | GET | /api/biblio/bibtex | - | - | F-06 | works_clean_v2 batch | public | edge 24h | Bulk export; max 500/req | - | Supabase | PLANLI | F3 | B: B-65
66 | B-66 | GET | /api/biblio/csl-json | - | - | F-06 | works_clean_v2 | public | edge 24h | CSL-JSON Zotero/Mendeley uyumlu | - | Supabase | PLANLI | F3 | B: B-66
GRUP 11 — NOTIFY & WATCHLIST (B-71..B-73, B-80..B-82)
GRUP 12 — AUTHOR ENDPOINTS (B-74..B-76)
GRUP 13 — CITATION GRAPH (B-77..B-79)
GRUP 14 — WATCHLIST & LIBRARY (B-80..B-85)
83 | B-83 | GET | /api/library | /api/reading-list | reading_list.py:32 | F-03 | fact_user_library (cross-project) | jwt | edge 60s | Tum bookmarklar tek view | - | Supabase | LIVE | F3 | A: reading_list.py:32 (GET) + B-83 (renamed library->reading-list)
GRUP 15 — PUBLIC API (B-86..B-87)
GRUP 16 — PIVOT/POST-RENCBER YENI ENDPOINTS (B-021 + F13)
88
89 | YENI | POST | /api/q/literature-review | /api/q/literature-review | q.py:198 | - | vitrin_literature role | public | - | Vitrin Q3 7-tag K=25 | Flash | Pinecone+Supabase | LIVE | F2-D1 | A: q.py:198 — Q3 vitrin canon
90 | YENI | POST | /api/q2 | /api/q2 | q.py:283 | - | - | public | - | Deneysel Q2 | - | - | LIVE | F2 | A: q.py:283
91 | YENI | POST | /api/chat | /api/chat | chat.py:37 | - | llm_service | jwt | - | Sohbet (Q akisi disinda) | Flash | - | LIVE | F3 | A: chat.py:37
92
93 | YENI | POST | /api/research-area/anchor-candidates | /api/research-area/anchor-candidates | research_area.py:84 | - | anchor_finder | jwt | - | Capa adaylari | Flash | Pinecone | LIVE | PIVOT | A: research_area.py:84
94 | YENI | POST | /api/top5 | /api/top5 | top5.py:46 | - | curator + presenter | jwt | - | 2.2 Top-5 oneri (PLANLI: Top-25) | Flash | Pinecone+Supabase | LIVE | F2-D2 | A: top5.py:46 + B-35 hatti | ✓ | ✓ | ✓ | ✓ | ✓
95 | YENI | POST | /api/project/{id}/research-area-init | /api/project/{id}/research-area-init | project.py:223 | - | project_service | jwt+owner | - | Proje arastirma alani init | Flash | Supabase | LIVE | PIVOT | A: project.py:223
96 | YENI | POST | /api/project/{id}/bibliometrics | /api/project/{id}/bibliometrics | project_bibliometrics.py:63 | - | bibliometric_service + openalex_polite | jwt+owner | - | 2.3 Bibliyometrik analiz | - | OpenAlex | LIVE | F3 | A: project_bibliometrics.py:63
97
98 | YENI | POST | /api/onboarding | /api/onboarding | onboarding.py:53 | - | dim service | jwt | - | Onboarding 4-alan + bridge | Flash | Supabase | LIVE | F3 (F5-S2) | A: onboarding.py:53 — KAPANDI 2026-05-04
99 | YENI | GET | /api/fields | /api/fields | dim.py:49 | - | dim_field | public | - | Onboarding alan dropdown | - | Supabase | LIVE | F3 | A: dim.py:49
100 | YENI | GET | /api/subfields | /api/subfields | dim.py:74 | - | dim_subfield | public | - | Onboarding alt-alan dropdown | - | Supabase | LIVE | F3 | A: dim.py:74
101 | YENI | POST | /api/waitlist | /api/waitlist | waitlist.py:67 | - | waitlist | public | - | Landing waitlist | - | Supabase | LIVE | F3 | A: waitlist.py:67
102 | YENI | POST | /api/tts | /api/tts | tts.py:42 | - | elevenlabs_tts | public | - | Vitrin Q3 TTS | - | ElevenLabs | LIVE | F3 | A: tts.py:42
103
104 | YENI | GET | /api/diary/timeline | /api/diary/timeline | diary.py:77 | - | diary_service | jwt | - | S1 Defter timeline | - | Supabase | LIVE | F13-S1 | A: diary.py:77
105 | YENI | PATCH | /api/diary/event/{id} | /api/diary/event/{event_id} | diary.py:97 | - | diary_service | jwt+owner | - | S1 event guncelle | - | Supabase | LIVE | F13-S1 | A: diary.py:97
106 | YENI | POST | /api/diary/pre-advisor-summary | /api/diary/pre-advisor-summary | diary.py:112 | - | diary_pre_advisor | jwt | - | S1 pre-advisor LLM ozet | Flash | - | LIVE | F13-S1 | A: diary.py:112
PLANLI — F13 (35 endpoint)
107 | F13-S2 | POST | /api/workshop/maturity | - | - | 5.1 | - | jwt+owner | - | 5.1 Yayin formati maturity | Flash | - | PLANLI | F13-S2 | B: F13 plan §2
108
109 | F13-S3 | POST | /api/workshop/paraphrase | - | - | 5.3 | engine/style/{tr,en,id}.json | jwt+owner | - | 5.3 Akademik dil paraphrase | Flash | - | PLANLI | F13-S3 | B: F13 plan §2
110 | F13-S3 | POST | /api/workshop/paraphrase-decision | - | - | 5.3 | silent_learning (0026) | jwt+owner | - | 5.3 Decision log | - | Supabase | PLANLI | F13-S3 | B: F13 plan §2
111 | F13-S4 | POST | /api/workshop/citation-format | - | - | 5.4, 3.1 | engine/citation/{apa,vancouver,ieee,chicago,mla}.py | jwt+owner | - | 5.4 Atif format (B-64 RENCBER ile ortusur) | - | - | PLANLI | F13-S4 | B: F13 plan §2 — RENCBER B-64 ile ortusur
112 | F13-S4 | POST | /api/workshop/citation-validate | - | - | 5.4 | engine/citation/* | jwt+owner | - | 5.4 Atif dogrulama | - | - | PLANLI | F13-S4 | B: F13 plan §2
113 | F13-S4 | POST | /api/workshop/citation-translate | - | - | 5.4 | engine/dictionary/{tr,en,id}.json | jwt+owner | - | 5.4 3-dil ceviri | Flash | - | PLANLI | F13-S4 | B: F13 plan §2
114 | F13-S4 | POST | /api/workshop/citation-doi-resolve | - | - | 5.4 | - | jwt+owner | - | 5.4 DOI cozumleme | - | OpenAlex | PLANLI | F13-S4 | B: F13 plan §2
115 | F13-S5 | POST | /api/workshop/topic-proposals | - | - | 5.2 | llm_service | jwt+owner | - | 5.2 Konu onerileri | Flash | - | PLANLI | F13-S5 | B: F13 plan §2
116
117 | F13-S6 | POST | /api/workshop/manuscript/generate-section | - | - | 6.1 | manuscript_section (0027) | jwt+owner | - | 6.1 Bolum uret | Pro | - | PLANLI | F13-S6 | B: F13 plan §2
118 | F13-S6 | POST | /api/workshop/manuscript/refine | - | - | 6.1 | manuscript_section | jwt+owner | - | 6.1 Bolum iyilestir | Pro | - | PLANLI | F13-S6 | B: F13 plan §2
119 | F13-S6 | GET | /api/workshop/manuscript/{id} | - | - | 6.1 | manuscript_section | jwt+owner | - | 6.1 Bolum oku | - | Supabase | PLANLI | F13-S6 | B: F13 plan §2
120
121 | F13-S7 | POST | /api/workshop/defense/generate-questions | - | - | 6.2 | defense_session (0028) | jwt+owner | - | 6.2 Soru havuzu | Pro | - | PLANLI | F13-S7 | B: F13 plan §2
122 | F13-S7 | POST | /api/workshop/defense/suggest-jury | - | - | 6.2 | defense_session | jwt+owner | - | 6.2 Juri oneri | Flash | - | PLANLI | F13-S7 | B: F13 plan §2
123 | F13-S8 | POST | /api/workshop/journal-suggest | - | - | 6.3 | engine/journals/review_distribution.json | jwt+owner | - | 6.3 Dergi oneri | Flash | - | PLANLI | F13-S8 | B: F13 plan §2
124
125 | F13-S8 | POST | /api/workshop/personal-feedback | - | - | 6.3 | llm_service | jwt+owner | - | 6.3 Bireysel geri bildirim | Flash | - | PLANLI | F13-S8 | B: F13 plan §2
126 | F13-S9 | POST | /api/defense/reviewer-3persona | - | - | 6.4 | engine/personas/journal/* | jwt+owner | - | 6.4 3-persona hakem | Pro | - | PLANLI | F13-S9 | B: F13 plan §2
127 | F13-S9 | POST | /api/defense/statcheck | - | - | 6.4 | engine/statcheck/multilingual.json | jwt+owner | - | 6.4 Statistik check | - | - | PLANLI | F13-S9 | B: F13 plan §2
128
129 | F13-S10 | POST | /api/defense/jury-question | - | - | 6.5 | engine/personas/jury/* | jwt+owner | - | 6.5 Juri sorusu (B-56 critique ile ortusur) | Pro | - | PLANLI | F13-S10 | B: F13 plan §2 — B-56 hatti
130 | F13-S10 | POST | /api/defense/hyde-fanout-rerank | - | - | 6.5 | jury | jwt+owner | - | 6.5 HyDE fanout + rerank | Pro | Pinecone+Cohere | PLANLI | F13-S10 | B: F13 plan §2 — Cohere R1 risk
131 | F13-S10 | POST | /api/defense/answer-score | - | - | 6.5 | engine/jury/reaction_thresholds.json | jwt+owner | - | 6.5 Cevap skoru | Flash | - | PLANLI | F13-S10 | B: F13 plan §2
132 | F13-S10 | POST | /api/defense/consistency-check | - | - | 6.5 | jury | jwt+owner | - | 6.5 Tutarlik | Flash | - | PLANLI | F13-S10 | B: F13 plan §2
133 | F13-S10 | POST | /api/defense/jury-decision-band | - | - | 6.5 | jury | jwt+owner | - | 6.5 Karar bandi | - | - | PLANLI | F13-S10 | B: F13 plan §2
134 | F13-S11 | POST | /api/workshop/synthesize | - | - | 3.4 | llm_service | jwt+owner | - | 3.4 Sentez | Pro | - | PLANLI | F13-S11 | B: F13 plan §2
135
136 | F13-S11 | POST | /api/workshop/originality | - | - | 4.3 | llm_service | jwt+owner | - | 4.3 Ozgunluk | Flash | - | PLANLI | F13-S11 | B: F13 plan §2
137 | F13-S11 | POST | /api/workshop/compare | - | - | 4.4 | llm_service | jwt+owner | - | 4.4 Karsilastirma | Flash | - | PLANLI | F13-S11 | B: F13 plan §2
138
139 | F13-S12 | POST | /api/project/{id}/research-area/reset | - | - | 2.1 | project_service | jwt+owner | - | 2.1 Reset (B-37 unlock hatti) | - | Supabase | PLANLI | F13-S12 | B: F13 plan §2 — RENCBER B-37 hatti
140 | F13-S13 | POST | /api/completion/snapshot | - | - | S2 | engine/completion/calculator | jwt+owner | - | S2 Tamamlama snapshot | - | Supabase | PLANLI | F13-S13 | B: F13 plan §2
141 | F13-S13 | POST | /api/feedback/project-completion | - | - | S2 | - | jwt+owner | - | S2 Geri bildirim | Flash | - | PLANLI | F13-S13 | B: F13 plan §2

## Auth & Tier
# | Konu | Detay | Yer | Bagli Endpoint/Sayfa | Karar / Karar Kaynak | Kanit Seviyesi | Durum
═══ AUTH FLOW (Clerk → Supabase RLS) ═══
AF-1 | Frontend Clerk SDK | @clerk/nextjs (App Router); ClerkProvider root layout; <SignIn/>, <SignUp/> components | web/src/app/layout.tsx (henüz yok) | Tüm korunan sayfalar | B-022 (2026-05-10) | C: doğrulayamıyorum (paket henüz yüklenmedi) | PLANLI
AF-2 | Middleware koruma | clerkMiddleware() — public routes hariç hepsini koru | web/middleware.ts (yeni) | /(app)/* tüm sayfalar | B-022 | C: doğrulayamıyorum | PLANLI
AF-3 | JWT template | Clerk Dashboard'da Supabase template aktif et — JWT'ye `role: authenticated` claim | Clerk Dashboard (manuel) | Tüm Supabase RLS kontrolleri | B-022 | C: Clerk Dashboard config | PLANLI
AF-4 | Backend JWT verify | FastAPI dependency: Clerk JWKS endpoint'ten public key + JWT verify (jose lib) | api/middleware/auth.py (yeni) | Tüm jwt-required endpoint | B-022 | C: implementasyon yok | PLANLI
AF-5 | Webhook → Supabase upsert | Clerk webhook user.created/updated/deleted → /api/webhooks/clerk → user_profiles upsert | api/routes/webhooks.py (yeni) | 0012 user_profiles (B) | B-022 | C: webhook yapısı icat edilmedi, plan | PLANLI
AF-6 | Supabase RLS (auth.jwt()) | RLS policies Clerk JWT sub claim'i okuyup user_id eşleştirir; auth.uid() yerine current_setting('request.jwt.claims', true)::json->>'sub' | db/migrations/* policies | Tüm RLS-li tablo (~20) | B-022 | C: tüm policies refactor gerek | PLANLI
AF-7 | Supabase Auth eski yapı | SUPABASE_JWKS_URL (config.py:25) artık kullanılmayacak; .env'den çıkarılacak | .env.example:25 + api/config.py:25 | — | B-022 SUPERSEDED | A: config.py:25 + .env.example:25 | SUPERSEDED
═══ 3-TIER × IZIN MATRISI (0012 user_tier ENUM) ═══
Tier | Açıklama | Günlük arama | Günlük LLM çağrı | Kayıtlı paper limit | Proje limit | Kanıt Seviyesi | Durum
ogrenci | Default tier (0012:85 SET DEFAULT 'ogrenci') | TBD | TBD | TBD | TBD | A: 0012:85 default | TBD-KOTA
arastirmaci | Orta tier | TBD | TBD | TBD | TBD | A: 0012:71 ENUM | TBD-KOTA
profesyonel | Üst tier | TBD | TBD | TBD | TBD | A: 0012:71 ENUM | TBD-KOTA
═══ ACIK SORULAR (Bilinen Borclar'a taşınacak) ═══
AQ-1 | Tier × kota tablosu | Her tier için günlük arama/LLM çağrı/disk limiti — sayısal hedefler nedir? | — | — | Omer karar verecek | C | ACIK
AQ-2 | Anonim kullanıcı | Login öncesi /api/q çağrılabilir mi? Şu an public mı jwt mı? | search.py / q.py | Vitrin Q sayfası | Omer karar verecek | C | ACIK
AQ-3 | Webhook secret rotation | Clerk webhook signing secret — env nasıl rotate edilir? | — | — | deploy plan | C | ACIK
AQ-4 | Supabase RLS migration | Mevcut auth.uid() kullanan policies bulunup refactor — hangi migration'lar? | db/migrations/0010+ | Tüm RLS tablo | Sercan/F13-S? | C | ACIK
AQ-5 | Onboarding tier seç | Yeni user signup'ta tier nasıl seçilir? Default ogrenci, sonra upgrade? | 0012 + onboarding sayfa | /onboarding | ürün karar | C | ACIK
AF-8 | tier_gate middleware (KEŞFEDİLDİ) | api/middleware/tier_gate.py + Tier enum kullanımı (q.py:6 import); endpoint dekoratörü ile tier kontrolü | api/middleware/tier_gate.py | /api/q (q.py:6 import) + diğerleri TBD | Mevcut yapı (Clerk öncesi) | A: q.py:6 + ls | LIVE

## Cron & Scheduled
# | Cron Adı | Frequency | Sorumluluk | Dosya/Yer | Bagli Tablo/Servis | Provider | Kanit Seviyesi | Durum | Faz
═══ MEVCUT (B/A kanıtlı) ═══
C-1 | HF Inference keep-alive | 240s (4dk) | HF Endpoint scale-to-zero soğumasın diye ping; cold start cezası ~30s'den kaçınır | .github/workflows/hf_keepalive.yml | HF Endpoint (Qwen2.5-7B) | GitHub Actions | B: F7_quality_deploy_pilot.md:33 | PLANLI | F7
C-2 | Papers lazy-fill | 1x oneshot (Day 4 wrap) | fact_paper_id_card.title → papers.title batch UPSERT (~24.87M satır, ~6h) | api/workers/papers_lazy_fill.py | papers / fact_paper_id_card | Manuel/F2-D4 | B: F2_day3_4:44 + F2_day2_4:590 | PLANLI | F2-D4
═══ F13 CRON HEDEFI (6 cron — Q3 ACIK) ═══
C-3 | [F13 cron #1] — isim TBD | TBD | F13 plan §1: '6 cron job kayıtlı + smoke' — isim/freq belirsiz | TBD | TBD | Q3: Render scheduled / Supabase cron / GH Actions? | B: F13:21 + B: Q3 açık | TBD | F13-S14
C-4 | [F13 cron #2] — isim TBD | TBD | F13 plan; isim belirsiz | TBD | TBD | Q3 açık | B: F13:79 | TBD | F13-S14
C-5 | [F13 cron #3] — isim TBD | TBD | F13 plan; isim belirsiz | TBD | TBD | Q3 açık | B: F13:79 | TBD | F13-S14
C-6 | [F13 cron #4] — isim TBD | TBD | F13 plan; isim belirsiz | TBD | TBD | Q3 açık | B: F13:79 | TBD | F13-S14
C-7 | [F13 cron #5] — isim TBD | TBD | F13 plan; isim belirsiz | TBD | TBD | Q3 açık | B: F13:79 | TBD | F13-S14
C-8 | [F13 cron #6] — isim TBD | TBD | F13 plan; isim belirsiz | TBD | TBD | Q3 açık | B: F13:79 | TBD | F13-S14
═══ ACIK SORU ═══
AQ-C1 | Q3: Cron provider seçimi | — | Render scheduled jobs MU, Supabase cron MU, ayrı GitHub Actions MU? F13-S14 GREEN için zorunlu | — | — | Omer/Sercan karar | B: F13:156 | ACIK | F13-S14

## Deploy & Infra
# | Bileşen | Provider | Region/Tier | Scale Config | ENV Key | Maliyet (tahmin) | Bagli Servis | Kanit Seviyesi | Durum
D-1 | Frontend (Next.js 16) | Vercel | Hobby/Pro TBD | Edge functions + ISR | VERCEL_TOKEN (deploy) | Hobby $0 / Pro $20/ay | Clerk + Supabase + API | B: F7:31 | PLANLI
D-2 | Backend (FastAPI) | Render | Free/Starter TBD | ALWAYS restart (DM-013 + DM-014) | RENDER_API_KEY (deploy) | Starter $7/ay | Supabase + Pinecone + HF + LiteLLM | B: F7:31 | PLANLI
D-3 | DB + Auth + Storage | Supabase | EU TBD (region kararsız) | Managed Postgres + RLS | SUPABASE_URL + SECRET_KEY | Free 500MB / Pro $25/ay | FastAPI + (Clerk JWT) | A: .env.example:1-7 | LIVE
D-4 | Vector DB | Pinecone | eu-west-1 (papers-bgem3) | Serverless 1024-d cosine; 24.87M vec | PINECONE_API_KEY | Serverless ~$0.12/M query | FastAPI search/recommend | B: project_papermind_current.md | LIVE
D-5 | LLM Inference | HF Inference Endpoint | EU (TBD) | Scale-to-Zero + 240s keep-alive (DM-010) | HF_TOKEN | $0.50/saat aktif (TBD) | Listener/Curator/Presenter | B: F7:33,99 | PLANLI
D-6 | LLM (managed) | LiteLLM proxy → Gemini | Global | Flash/Pro 2.5 router | GEMINI_API_KEY | Flash $0.075/M tok / Pro $1.25/M | PoolRouter + Curator | B: project_papermind_current | LIVE
D-7 | Auth | Clerk (B-022) | Global | @clerk/nextjs + JWKS | CLERK_PUBLISHABLE_KEY + CLERK_SECRET_KEY | Free 10K MAU / Pro $25/ay | Frontend + FastAPI + Supabase RLS | C: yeni karar (2026-05-10) | PLANLI
D-8 | Cron provider | Q3 ACIK | — | — | — | — | F13-S14 cron job'ları | B: F13:156 | TBD
D-9 | Reranker | HF Inference Endpoint | EU (TBD) | BGE-v2-m3 reranker | HF_TOKEN | Aynı D-5 endpoint | Reranker katman | B: project_papermind_current | PLANLI
D-10 | Embedding compute | Colab Pro+ × 3 | Manuel batch | BGE-M3 1024-d | — | Colab Pro+ $50/ay × 3 = $150 | Pinecone yükleme | B: CLAUDE.md §6 | LIVE
D-11 | External enrich | OpenAlex + Crossref + Unpaywall | Public API | Polite pool | — | Free (rate-limited) | /api/enrich + /api/external/* | A: enrich.py:56 | LIVE
D-12 | Logs / errors | TBD (Sentry?) | — | — | — | Free tier | Tüm backend | C: karar yok | TBD
D-13 | Cache (Redis) | Upstash? (RENCBER FAZ 2) | — | L1 90gün TTL | — | Free 10K req/gün | Hot endpoints | C: RENCBER planı, karar yok | TBD

## Hata & Limit
# | Endpoint Grubu | Tipik Hata | HTTP Code | Retry Policy | Rate Limit | Circuit Breaker | Kanit Seviyesi | Durum
E-1 | /api/q + /api/q2 (Vitrin) | Pinecone timeout / LLM timeout / RLS reject | 504/429/403 | TBD (idempotent ama maliyetli) | TBD per-tier | TBD | C: politika yok | TBD
E-2 | /api/search + /search/hybrid | Pinecone timeout / sparse encoder fail | 504/500 | TBD (idempotent) | TBD | TBD | C | TBD
E-3 | /api/llm/* (Listener/Curator/Presenter) | LiteLLM Gemini 429 / context overflow | 429/400 | TBD (jitter backoff önerilir) | TBD per-tier kota | TBD | C | TBD
E-4 | /api/enrich + /external/* | OpenAlex/Crossref 429 / network | 429/503 | Polite pool delay var (enrich.py:56 A) | OpenAlex 10/sec polite | TBD | A: enrich.py polite | PARTIAL
E-5 | /api/notes + /api/projects (write) | RLS reject / quota exceeded | 403/409/507 | Yok (non-idempotent) | TBD per-tier disk | — | C | TBD
E-6 | /api/webhooks/clerk (B-022) | Signing secret mismatch / replay | 401/409 | Yok (idempotency key zorunlu) | Clerk tarafı | — | C: yapı yok | PLANLI
E-7 | Frontend → Backend (genel) | CORS / 401 expired token | 401/403 | Token refresh: Clerk SDK auto | — | — | C: B-022 sonrası | PLANLI
E-8 | HF Endpoint (Listener/Reranker) | Cold start (~30s) / scale-up timeout | 503/504 | Keep-alive 240s (C-1) | — | TBD: cold start gözlemi | B: F7:33 | PARTIAL
═══ ACIK SORULAR ═══
EQ-1 | Tier × rate limit sayıları | Tier başına /sec, /dk, /gün limiti — sayı? | — | — | Omer | — | C | ACIK
EQ-2 | Sentry mı, kendi log mu | D-12 ile bağlı; error tracking provider seçimi | — | — | — | — | C | ACIK
EQ-3 | Idempotency key standardı | Write endpoint'lerde X-Idempotency-Key zorunlu mu? | — | — | — | — | C | ACIK

## Traceability Matrisi
F-ID (Sayfa) | Sayfa Adı | B-ID(s) | Endpoint Path | Migration | Engine/Servis | Auth | Durum
- | — | B-28 | GET /api/auth/me | dim_user + projects count | — | jwt | PLANLI
2.1 | — | F13-S12 | POST /api/project/{id}/research-area/reset | project_service | — | jwt+owner | PLANLI
3.4 | — | F13-S11 | POST /api/workshop/synthesize | llm_service | — | jwt+owner | PLANLI
4.3 | — | F13-S11 | POST /api/workshop/originality | llm_service | — | jwt+owner | PLANLI
4.4 | — | F13-S11 | POST /api/workshop/compare | llm_service | — | jwt+owner | PLANLI
5.1 | — | F13-S2 | POST /api/workshop/maturity | - | — | jwt+owner | PLANLI
5.2 | — | F13-S5 | POST /api/workshop/topic-proposals | llm_service | — | jwt+owner | PLANLI
5.3 | — | F13-S3, F13-S3 | POST /api/workshop/paraphrase ¦ POST /api/workshop/paraphrase-decision | silent_learning (0026) ¦ engine/style/{tr,en,id}.json | — | jwt+owner | PLANLI
5.4 | — | F13-S4, F13-S4, F13-S4 | POST /api/workshop/citation-validate ¦ POST /api/workshop/citation-translate ¦ POST /api/workshop/citation-doi-resolve | - ¦ engine/dictionary/{tr,en,id}.json ¦ engine/citation/* | — | jwt+owner | PLANLI
5.4, 3.1 | — | F13-S4 | POST /api/workshop/citation-format | engine/citation/{apa,vancouver,ieee,chicago,mla}.py | — | jwt+owner | PLANLI
6.1 | — | F13-S6, F13-S6, F13-S6 | POST /api/workshop/manuscript/generate-section ¦ POST /api/workshop/manuscript/refine ¦ GET /api/workshop/manuscript/{id} | manuscript_section ¦ manuscript_section (0027) | — | jwt+owner | PLANLI
6.2 | — | F13-S7, F13-S7 | POST /api/workshop/defense/generate-questions ¦ POST /api/workshop/defense/suggest-jury | defense_session (0028) ¦ defense_session | — | jwt+owner | PLANLI
6.3 | — | F13-S8, F13-S8 | POST /api/workshop/journal-suggest ¦ POST /api/workshop/personal-feedback | engine/journals/review_distribution.json ¦ llm_service | — | jwt+owner | PLANLI
6.4 | — | F13-S9, F13-S9 | POST /api/defense/reviewer-3persona ¦ POST /api/defense/statcheck | engine/statcheck/multilingual.json ¦ engine/personas/journal/* | — | jwt+owner | PLANLI
6.5 | — | F13-S10, F13-S10, F13-S10, F13-S10, F13-S10 | POST /api/defense/jury-question ¦ POST /api/defense/hyde-fanout-rerank ¦ POST /api/defense/answer-score ¦ POST /api/defense/consistency-check ¦ POST /api/defense/jury-decision-band | engine/jury/reaction_thresholds.json ¦ engine/personas/jury/* ¦ jury | — | jwt+owner | PLANLI
F-01 | — | B-25 | GET /api/health + /api/version | manifest hash + Pinecone health | — | public | PLANLI
F-02 | — | B-58 | GET /api/llm/limit-status | fact_user_quota | — | jwt | PLANLI
F-03 | — | B-31, B-32, B-33, B-34, B-36, B-37, B-83 | GET/POST /api/projects ¦ GET/PATCH/DEL /api/projects/{id} ¦ GET/POST/DEL /api/projects/{id}/papers ¦ GET/POST/DEL /api/projects/{id}/topics ¦ POST /api/projects/{id}/topic-lock ¦ POST /api/projects/{i | project_topics + dim_theme ¦ project_papers + works_clean_v2 ¦ fact_user_project + project_papers ¦ project_topics ¦ fact_user_project (B-002) / proje | — | jwt+owner, jwt | PLANLI, LIVE (partial), LIVE, PLANLI (F13-S12)
F-04 | — | B-35, B-39, B-40 | POST /api/topic/suggest ¦ POST /api/search/semantic ¦ POST /api/search/hybrid | Pinecone dense+sparse + BM25 fallback ¦ Pinecone (W-28) + BGE-M3 query encode ¦ dim_theme + Pinecone (W-28) + PMID hierarchy | — | jwt | LIVE
F-04, F-05 | — | B-01 | POST /api/search | fact_paper_id_card (W-36) + Pinecone (W-28) + sentence (W-24) + quality (W-09) | — | public | LIVE
F-06 | — | B-02, B-54, B-55, B-64, B-65, B-66 | GET /api/papers/{paper_id} ¦ POST /api/llm/summarize ¦ POST /api/llm/explain ¦ GET /api/biblio/cite-as/{format} ¦ GET /api/biblio/bibtex ¦ GET /api/biblio/csl-json | fact_paper_abstract_flags + Gemini ¦ works_clean_v2 + dim_author + dim_journal ¦ works_clean_v2 (W-01) + fact_paper_id_card (W-36) ¦ fact_paper_senten | — | public, jwt | PLANLI, LIVE, PLANLI (F13-S4)
F-07 | — | B-06 | GET /api/papers/{id}/refs | fact_citation_edge (W-10) + works_clean_v2 | — | public | LIVE
F-08 | — | B-09, B-59, B-60, B-61, B-62, B-63 | GET /api/papers/{id}/bibcoupling ¦ GET /api/recommend/related ¦ GET /api/recommend/diverse ¦ GET /api/recommend/cross-domain-flag ¦ GET /api/recommend/confidence ¦ POST /api/recommend/explain | fact_paper_bibcoupling_top50 (W-14) ¦ Pinecone metadata D/F/S + topic_lock ¦ recommendation trace + LLM ¦ q_weak + v_conf + sim score ¦ interdisc + re | — | public, jwt | PLANLI, LIVE
F-12 | — | B-23 | GET /api/gap-matrix | fact_gap_matrix (W-27) | — | public | LIVE
F-13 | — | B-56 | POST /api/llm/critique | paper + bibcoupling + cited authors | — | jwt | PLANLI (F13-S10)
F-14 | — | B-43, B-44, B-45, B-46 | GET/POST /api/notes ¦ GET/PATCH/DEL /api/notes/{id} ¦ POST /api/notes/{id}/highlight ¦ GET /api/projects/{id}/notes | fact_user_note ¦ fact_user_note (B-002) ¦ fact_user_note + projects ¦ fact_user_highlight + fact_paper_sentence (W-24) | — | jwt+owner, jwt | PLANLI, LIVE (partial), LIVE
S2 | — | F13-S13, F13-S13 | POST /api/completion/snapshot ¦ POST /api/feedback/project-completion | - ¦ engine/completion/calculator | — | jwt+owner | PLANLI
═══ ORPHAN (F-ID'siz endpoint'ler) ═══